FOUNDER'S PLAYBOOK

Modular-Liner Trail Running Shorts

D2C Brand — Go-To-Market Executive Summary

| 60,000+ | 361 | 50 | 12 |
| --- | --- | --- | --- |
| Words of Strategy | Tasks Mapped | Gaps Analysed | Subprojects |

March 2026 | Confidential

# 1. THE BUSINESS IN ONE PAGE

This playbook condenses 60,000+ words of GTM strategy into the prioritised actions you need to launch modular trail running shorts from Lahore to UK and EU customers. Read this document first. Reference the detailed subproject files only when executing specific tasks.

## 1.1 What You're Building

Product: A modular trail running short system — outer shell + detachable compression liner with 6-point snap attachment. Wear either piece alone or snap them together.

Price: Outer £28 | Liner £15 | System Bundle £39 (saves £4) | Double Bundle £49 (saves £9)

Market: UK trail runners (#1), French trail runners (#2), broader EU (#3)

Channel: DTC via Shopify (primary) + trail events (secondary) + UK indie running shop wholesale (tertiary)

Manufacturing: Outsource to Sialkot sportswear factory. Fabric from Shaoxing, China. Family factory in Lahore for Phase 2.

First Run: 200-300 units depending on available capital (see Section 2)

Differentiators: Modular system at half Path Projects' price, women's from Day 1, XS-3XL inclusive, C0 PFC-free DWR, EU-first via Pakistan DCTS 0% duty.

## 1.2 The Numbers That Matter

| Metric | Target | Source |
| --- | --- | --- |
| System bundle contribution margin (UK) | 42.2% | P4A.4 |
| Year 1 revenue (base case) | £7,000-10,000 | P4A.10 |
| Break-even orders | ~303 orders | P4A.9 |
| Total Year 1 cash required | £23,640-27,940 | P7A.9 |
| Target CAC (blended) | £15-25 | P4A.7 |
| Target repeat purchase rate (12 months) | 30-40% | P10A.9 |
| Email list target (pre-launch) | 200-300 subscribers | P5A.1 |
| Monthly fixed costs | ~£120/month | P4A.11 |
| Bundle attach rate target | >60% of orders | P4A.8 |

# 2. THE 5 GO/NO-GO GATES

These must be resolved IN ORDER before committing any production budget. Each gate determines whether the project proceeds, pivots, or stops. Completing all 5 gates takes 2-3 weeks and costs under £500.

## Gate 1: Capital Confirmation (Day 1)

Complete the capital assessment worksheet in the Gap Fixes B01 document. Determine your scenario:

| Your Capital | Scenario | Run 1 Size | Gender | Marketing |
| --- | --- | --- | --- | --- |
| £5-8K | A: Bootstrap | 150-200 units | Single gender | £500-1K |
| £10-15K | B: Serious | 250-300 units | Both genders | £2-3K |
| £20-30K | C: Comfortable | 300 units | Both genders | £3-5K |
| £30K+ | D: Well-funded | 300 units | Full range | £5K+ |

Reference: P7A Addendum + Gap Fix B01

## Gate 2: Customer Validation (Days 3-4)

Talk to 10 trail runners face-to-face. Use the interview script in Gap Fix B15. Apply the GO/PIVOT/STOP framework:

GO: 7+ of 10 interested in concept, average purchase intent 7+/10, price reaction positive.

PIVOT: 4-6 of 10 interested. Adjust price, positioning, or target audience before proceeding.

STOP: 0-3 of 10 interested. Save your money. This is the most valuable possible Saturday morning.

## Gate 3: Brand Name (Day 5)

Select from your P1A shortlist. Screen for .com domain + trademark availability. Test with runners from Gate 2. DECIDE. Purchase domains + handles + file UKIPO (£170) within 24 hours. Every week without a name delays the entire project by one week.

## Gate 4: Supply Chain Verification (Weeks 2-3)

Contact 3 Sialkot factories + 6-8 Chinese fabric suppliers simultaneously. Score each on the matrices in Gap Fix A01/A03. Order fabric samples. Audit family factory capability. All answers must be YES at Week 3 GO/NO-GO gate before committing production budget.

## Gate 5: Form UK Ltd + Register VAT (Week 1-2)

Incorporate UK Ltd online (1-2 days). Open Wise Business account (1-3 weeks verification). Apply for voluntary VAT registration (2-8 weeks processing — start early). Register EORI number. This gates all payments, imports, and store setup.

# 3. MASTER EXECUTION TIMELINE

This is the critical path from today to launch day. Sampling timeline assumes 22-26 weeks with buffer (Gap Fix A05). Parallel workstreams claw back 4-6 weeks.

| PHASE 1: VALIDATION | Weeks 1-3 | Complete 5 Go/No-Go Gates. Capital confirmed. 10 customer interviews done. Brand name selected. Factories contacted. UK Ltd formed. |
| --- | --- | --- |

| PHASE 2: PRODUCT DEV | Weeks 3-26 | Pattern development. Sampling (6-9 rounds with buffer). Fabric procurement. Snap mechanism validation (Week 9 gate). PP sample approval. |
| --- | --- | --- |

| PHASE 3: PRE-LAUNCH | Weeks 12-26 (parallel) | Build Shopify store. Install all tracking. Create content. Build email waitlist (target 200-300). Start social media. Seed product to 20-25 influencers. PR outreach. |
| --- | --- | --- |

| PHASE 4: PRODUCTION | Weeks 24-28 | Cut and sew 200-300 units. QC inspection. Pack and ship to UK via air freight. Clear customs. |
| --- | --- | --- |

| PHASE 5: LAUNCH | Week 30 | Remove Shopify password page. Launch email blast. Social media launch. Begin daily fulfillment. Monitor analytics. |
| --- | --- | --- |

| PHASE 6: FIRST 90 DAYS | Weeks 30-42 | Daily fulfillment. Collect reviews. Post-purchase surveys. Reorder decision (Week 32-33 if >3 units/day). Attend 2-3 trail events. Start paid ads if 30+ organic sales. |
| --- | --- | --- |

Critical path bottleneck: SAMPLING. If sampling runs to 12 rounds, launch delays 2-3 months. The Week 9 Snap Decision Gate is the most important single milestone — if snaps don't work, pivot to Velcro immediately.

# 4. UNIT ECONOMICS CHEAT SHEET

Memorise these numbers. They determine every pricing, marketing, and channel decision.

|  | Outer (£28) | Liner (£15) | Bundle (£39) | Double (£49) |
| --- | --- | --- | --- | --- |
| Revenue ex-VAT | £23.33 | £12.50 | £32.50 | £40.83 |
| Total variable costs (UK) | £14.57 | £11.68 | £18.78 | £22.96 |
| UK contribution margin | £8.76 (37.6%) | £0.82 (6.6%) | £13.72 (42.2%) | £17.87 (43.8%) |
| EU contribution margin | £3.14 (13.5%) | -£4.75 (LOSS) | £7.90 (24.3%) | £11.85 (29.0%) |
| Wholesale margin (50% RRP) | £7.50 (53%) | £3.57 (48%) | £9.07 (47%) | — |

Key insight: Standalone liner to EU LOSES £4.75 per order. Never sell liner-only to EU. Push bundles aggressively for all EU customers. The system bundle is where the business lives — 42.2% UK margin.

# 5. MARKETING PRIORITY STACK

What to do, in what order, with your limited time and budget. This is the complete marketing priority list from P5A, compressed into execution order.

| 1 | Pre-launch waitlist (8 weeks before) | £0 | Build 200-300 email subscribers via personal network, Instagram, parkrun, Reddit, Facebook groups. 7-email Klaviyo pre-launch flow. | P5A.1-P5A.3 |
| --- | --- | --- | --- | --- |

| 2 | Organic social (start Week 1) | £0 (time) | Instagram primary (3-4 Reels + 2-3 carousels/week), TikTok secondary (4-5 posts/week), Strava Club. Film once → edit for 3 platforms. | P5A.5-P5A.7 |
| --- | --- | --- | --- | --- |

| 3 | Micro-influencer seeding (Week 7-8) | £260-400 COGS | Gift 20-25 units to UK trail micro-influencers. No-strings gifting. Expect 10-15 content pieces. Primary value = UGC library. | P5A.12-P5A.14 |
| --- | --- | --- | --- | --- |

| 4 | PR outreach (Week 6-7) | £0 | Ship to Trail Running Magazine, Fast Running, UKRunChat, The Runner Beans. Press hook: 'women's from Day 1, modular, half the price of Path Projects'. | P5A.26 |
| --- | --- | --- | --- | --- |

| 5 | Trail events (Month 1+) | £200-500/event | Lakeland Trails, Centurion Running, parkrun presence. Sell in person at 50%+ margin. Best feedback channel. | Gap Fix A15 |
| --- | --- | --- | --- | --- |

| 6 | SEO blog content (Month 1+) | £0 (time) | 2 posts/month. Target: 'trail running shorts with liner', 'trail running shorts UK'. Results visible Month 4-6. | P5A.16-P5A.17 |
| --- | --- | --- | --- | --- |

| 7 | Wholesale outreach (Month 2-3) | £0 | Contact 8 UK indie running shops. 50% of RRP, MOQ 6 units. Diversifies revenue from 100% DTC. | Gap Fix A15/B02 |
| --- | --- | --- | --- | --- |

| 8 | Meta ads (Month 3+ IF 30 organic sales) | £50-100/month | Only after PMF proven. Broad UK targeting. UGC video creative. Retarget via Klaviyo email (free), not Meta audiences (too small). | P5A.19 |
| --- | --- | --- | --- | --- |

| 9 | Google Shopping (Month 4+) | £50-75/month | Standard Shopping (not PMAX). Expected CPC £0.60-1.20. | P5A.20 |
| --- | --- | --- | --- | --- |

# 6. LAUNCH CHECKLIST (T-7 DAYS)

Every item must be checked before removing the Shopify password page. Full detail in P8A.17.

TRACKING & ANALYTICS

☐  GA4 firing on all pages (verify via DebugView)

☐  Meta Pixel + Conversions API on Maximum mode

☐  TikTok Pixel installed

☐  Microsoft Clarity recording sessions

☐  Google Search Console verified + sitemap submitted

☐  UTM naming convention documented

STORE & PRODUCTS

☐  All products have images, descriptions, prices, HS codes, weights

☐  Bundle inventory sync tested (order bundle → component stock decreases)

☐  Test order placed and confirmed (Bogus Gateway or real)

☐  Express checkout (Shop Pay, Apple Pay) working

☐  Shopify Payments connected to Wise bank

SHIPPING & TAX

☐  UK + EU shipping zones configured with correct rates

☐  Free shipping over £40 threshold working

☐  VAT-inclusive pricing displaying correctly

☐  EU VAT rates correct in Shopify Markets

EMAIL & LEGAL

☐  Klaviyo connected — all pre-launch + post-launch flows ACTIVE

☐  SPF/DKIM/DMARC verified (use mail-tester.com)

☐  Privacy policy, T&Cs, returns policy published

☐  Cookie consent banner active (CookieYes)

☐  Judge.me review widget visible on product pages

MOBILE & SPEED

☐  Tested on actual phone (not emulator) — all pages work

☐  Lighthouse mobile score >80

☐  Add to Cart visible without scrolling on mobile

☐  Size guide opens as overlay, not new page

# 7. OPERATING RHYTHM

## 7.1 Every Morning (9 AM — 5 minutes)

Check Shopify: new orders, revenue, inventory remaining. Process orders by 11 AM. Check email for urgent support tickets. Glance at new reviews.

## 7.2 Every Sunday Evening (30 minutes)

Weekly business review: orders this week, revenue, AOV, bundle attach rate, inventory burn, marketing channel performance, new reviews, return count, and one priority for next week.

## 7.3 End of Each Month (1 hour)

Run P&L in Xero. Reconcile bank feed. Review inventory valuation. Check CX health score (repeat rate, review rating, return rate, NPS). Update cash flow forecast.

## 7.4 Quarterly (2 hours)

File VAT return via Xero MTD. Compare actual vs projected P&L. Review risk register. Check for regulatory changes (PFAS, GPSR).

# 8. THE 5 EXISTENTIAL RISKS

If any of these happen without mitigation, the business dies. Each has a prevention plan in the full documentation.

| Risk | Probability | Prevention |
| --- | --- | --- |
| K1: Cash runs out before Run 2 | 30-40% | Confirm capital at Gate 1. Maintain £8K+ reserve. Use pre-orders. Apply for Start Up Loan early. |
| K2: Product doesn't work | 15-25% | Extensive wear-testing. 200-cycle snap test. Week 9 gate: pivot to Velcro if snaps fail. Don't skip sampling rounds. |
| K3: Nobody buys | 20-30% | Validate at Gate 2 before production. If Month 6 <25 units: pivot to wholesale clearance. Don't order Run 2. |
| K4: Founder burns out | 25-35% | Set boundaries from Day 1. No email after 7 PM. One day off/week. 25 hr/week ceiling. Train a backup person. Hire VA at >30 hrs/week. |
| K5: Regulatory shutdown | 5-10% | REACH test before production. PFAS test from DWR supplier. Product liability insurance (£100-200/yr). Third-party verify. |

# 9. COMPLIANCE QUICK-REFERENCE

The legal requirements you MUST complete before launch, in priority order. Full detail in P9A.

| Requirement | Cost | Deadline | Priority | Notes |
| --- | --- | --- | --- | --- |
| Product liability insurance | £100-200/yr | Before launch | CRITICAL | Hiscox, Superscript, Simply Business |
| ICO registration (data controller) | £40/yr | Before collecting data | CRITICAL | ico.org.uk/registration |
| UK EORI number | Free | Before first import | CRITICAL | gov.uk |
| VAT registration (voluntary) | Free | 8 weeks before import | CRITICAL | HMRC — apply early, takes 2-8 weeks |
| REACH testing on fabrics | $300-600 | Before production | HIGH | SGS, Intertek, Bureau Veritas |
| UKIPO trademark (Class 25) | £170 | When name selected | HIGH | gov.uk/search-for-trademark |
| Textile labels (EN + FR) | Included in production | Before production | HIGH | Fibre comp + care + origin + Triman |
| Cookie consent banner | Free | Before launch | CRITICAL | CookieYes Shopify app |
| Privacy policy + T&Cs + Returns | Free (templates in P1G) | Before launch | CRITICAL | Shopify pages |
| Refashion + CITEO (France) | €350-850/yr | Before first French sale | HIGH | Via French mandataire |
| EU responsible person (GPSR) | €200-500/yr | Before first EU sale | HIGH | Via IOSS intermediary or service |
| EUIPO trademark | €850 | Within 3 months | HIGH | euipo.europa.eu |

Total compliance cost: £1,200-1,930 one-time + £613-1,403/year recurring.

# 10. FULL DOCUMENT INDEX

This playbook is your daily reference. The documents below are your deep-dive references for specific execution tasks.

| ID | Area | File Name | Contents |
| --- | --- | --- | --- |
| 00 | Master Tracker | Modular_Shorts_GTM_Master_Tracker.xlsx | 361 tasks, Gap Register, Critical Analysis |
| P0 | Market Research | P0A-P0H (8 documents) | Competitive intel, consumer pain points, EU research |
| P1 | Brand Development | P1A-P1G (9 documents) | Brand names, UK Ltd, content strategy, legal templates |
| P2A | Manufacturing | P2A_Product_Development_Manufacturing.md | Factory strategy, snap engineering, BOM, QC protocol |
| P2B | Fabric Sourcing | P2B_Fabric_Sourcing_Procurement.md | Alibaba sourcing, DWR spec, supplier matrix, quality gates |
| P2C | Sampling | P2C_Sampling_Fit_Testing_Production.md | Tech packs, grading, buffered timeline, compression |
| P3A | Supply Chain | P3A_Supply_Chain_Fulfillment.md | Freight, DCTS, carriers, returns, packaging |
| P4A | Pricing | P4A_Pricing_Financial_Modeling.md | Unit economics, break-even, bundle pricing, projections |
| P5A | Marketing | P5A_Digital_Marketing_Customer_Acquisition.md | Pre-launch, social, influencers, SEO, Klaviyo, France |
| P6A | Post-Launch Ops | P6A_Post_Launch_Operations.md | CS setup, fulfillment, returns, reviews, reorder framework |
| P7A | Financial Ops | P7A_Financial_Operations_Cash_Flow.md | Wise, Xero, VAT, PVA, cash flow, working capital |
| P8A | Tech Setup | P8A_Tech_Infrastructure_Analytics.md | Shopify, GA4, Meta Pixel, apps, speed, security |
| P9A | Legal | P9A_Legal_Compliance_Risk.md | Consumer law, REACH, GDPR, ASA, France Loi AGEC |
| P10A | Customer Experience | P10A_Customer_Experience_Retention.md | CX journey, retention, cross-sell, loyalty, NPS |
| GAP | Gap Analysis | Critical_Gap_Fixes (2 documents) | Capital, validation, name, sampling, revenue, supply chain |

Execute Gate 1 today. The rest follows.