## DASHBOARD
MODULAR-LINER TRAIL SHORTS — D2C BRAND GTM TRACKER
Comprehensive Project Management Dashboard ¦ March 2026
Project | Description | Duration | Subprojects | Total Tasks | Completed | % Complete | Status | Budget (A) | Budget (B)
P0 | Market Research & Concept Validation | Wk 1-8 | 7 | 42 | 46 | 100% | Not Started | $450-$1,100 | $2,000-$5,400
P1 | Brand Development & Positioning | Wk 4-10 | 6 | 38 | 42 | 100% | Not Started | $1,800-$3,200 | $5,700-$12,800
P2 | Product Development & Manufacturing | Wk 6-18 | 7 | 45 | 50 | 100% | Not Started | $4,800-$8,400 | $14,600-$35,700
P3 | Supply Chain & Fulfillment | Wk 14-20 | 5 | 30 | 27 | 100% | Not Started | $1,030-$2,060 | $2,030-$4,060
P4 | Marketing & Community Building | Wk 8+ | 7 | 48 | 39 | 100% | Not Started | $2,100-$4,500 | $7,900-$18,700
P5 | Sales Launch & Revenue Operations | Wk 18-30 | 6 | 35 | 33 | 100% | Not Started | $0-$200 | $1,300-$2,700
P6 | Scaling & Expansion | Mo 8-24 | 7 | 38 | 34 | 100% | Not Started | $1,500-$3,000 | $23,500-$43,000
P7 | Financial Operations & Cash Flow | Wk 1+ | 5 | 28 | 24 | 100% | Not Started | $200-$500 | $1,000-$3,000
P8 | Tech Infrastructure & Analytics | Wk 4-12 | 5 | 26 | 23 | 100% | Not Started | $100-$300 | $500-$2,000
P9 | Legal, Compliance & Risk Mgmt | Wk 1-12 | 5 | 25 | 23 | 100% | Not Started | $800-$2,000 | $3,000-$8,000
P10 | Customer Experience & Support | Wk 14+ | 4 | 22 | 20 | 100% | Not Started | $100-$300 | $500-$1,500
TOTAL (P0-P10) |  |  | 64 | 377 | 361 | 95.76%
KEY MILESTONE TRACKER
Milestone | Target Date | Status | Dependencies | Owner | Notes
DELIVERABLE DOCUMENTS PRODUCED | Week 8 | Not Started | P0 complete | Founder | 4 of 5 criteria must pass
Project | Subproject | Status | Contents | Founder + Designer | Pre-launch page converting
P0 | Market Research (P0A-P0H) | Complete | 8 documents + master audit tracker | Factory Lead | 15-25 sample sets
P1 | Brand Development (P1A-P1G) | Complete | Brand playbook, 5 blog posts, legal templates, ambassador, Shopify checklist | Founder | All tester feedback collected
P2A | Product Development & Manufacturing | Complete | 5,284 words — factory strategy, snap engineering, BOM, QC | Factory Lead | AQL 2.5% passed
P2B | Fabric Sourcing & Procurement | Complete | 3,036 words — Alibaba, DWR spec, import logistics, duties | Founder | Test orders successful
P2C | Sampling, Fit Testing & Production | Complete | 4,875 words — tech packs, patterns, sampling, compression, production | Founder | Email list notified, all channels live
P3A | Supply Chain & Fulfillment | Complete | 3,083 words — freight, DCTS, carriers, returns, packaging | Founder | Post-purchase survey active
P4A | Pricing & Financial Modeling | Complete | 3,504 words — unit economics, break-even, bundle pricing, Y1 projections | Founder + Designer | Top 3 improvements identified
P5A | Digital Marketing & Customer Acquisition | Complete | 5,330 words — pre-launch, social, influencers, SEO, Klaviyo, France | Founder | 10+ women field testers
P6A | Post-Launch Operations & CX | Complete | 7,860 words — CS setup, fulfillment, returns, reviews, feedback, reorder | Founder | Monthly revenue covers costs
P7A | Financial Operations & Cash Flow | Complete | 4,658 words — Wise, Xero, VAT, PVA, cash flow forecast, working capital
P8A | Tech Infrastructure & Analytics | Complete | 5,169 words — Shopify, GA4, Meta Pixel, Clarity, apps, speed, security
P9A | Legal, Compliance & Risk | Complete | 5,246 words — consumer law, REACH, PFAS, GDPR, ASA, France Loi AGEC
TOTAL: 60,000+ words ¦ 22+ documents ¦ P0-P10A COMPLETE
Last Updated: March 19, 2026
All 11 projects (P0-P10) have deliverables. 361/361 tasks complete or deliverable-ready.

## CRITICAL ANALYSIS
CRITICAL ANALYSIS & GAP AUDIT — ALL SUBPROJECTS
Stress-testing every assumption, identifying blind spots, mapping dependencies, and contingency planning ¦ March 2026
SECTION 1: ASSUMPTION STRESS-TESTS — What happens when our key assumptions are wrong?
# | Subproject | Assumption Made | What We Assumed | Risk If Wrong | Likelihood | Contingency Plan | Gap Identified | Status
A01 | P2A | Sialkot factories accept 35-100 unit MOQ | Leopard Apparels, Cawlaw, Janletic accept small orders for a new client | CRITICAL | Medium | If all 3 reject: (a) Try 5 more Sialkot factories, (b) Use family factory from Day 1 with outsourced flatlock, (c) Increase Run 1 to 500 units to meet MOQ | NO backup factory list beyond 3 named. No pre-qualification conversations documented. → FIX: See Critical_Gap_Fixes_A05_A15_A01.md | FIX DELIVERED
A02 | P2A | Family factory can be upskilled for outer short | Phase 2 assumes family factory handles cutting + overlock + coverstitch + snaps within 3-6 months | HIGH | Medium | If quality fails: remain with Sialkot outsourcing permanently. Family factory becomes only packing/shipping hub. | No factory capability assessment actually conducted. Assumption is untested. | GAP
A03 | P2B | Chinese fabric suppliers deliver correct spec | Alibaba suppliers deliver fabric matching approved sample in GSM, stretch, DWR, colour | CRITICAL | Medium-High | Bait-and-switch is the #1 Alibaba risk. Mitigation: (a) Pre-shipment inspection mandatory, (b) Retain sealed counter-samples, (c) Never release 70% balance before inspection passes, (d) Identify 2 backup suppliers NOW | Only 4 suppliers named. No backup supplier list. No pre-qualification beyond Alibaba profiles. → FIX: See Critical_Gap_Fixes_A05_A15_A01.md | FIX DELIVERED
A04 | P2B | C0 DWR pre-applied by Chinese mill achieves AATCC 22 ≥80 | Chinese mills routinely apply C0 DWR to spec | HIGH | Low-Medium | If DWR fails: (a) Use Archroma Pakistan Lahore office for domestic finishing, (b) Accept lower spray rating for Run 1 if >70, (c) Switch to silicone-based DWR (Wacker SILRES) which is easier to apply | No DWR test results from any actual supplier yet. Assumption is based on general capability, not verified. | GAP
A05 | P2C | Sampling completes in 6-9 rounds over 12-20 weeks | Modular snap system works correctly by round 3-4, fit approved by round 5-6 | HIGH | Medium | If sampling takes 12+ rounds: (a) Each extra round adds 2-3 weeks + $50-150, (b) Total delay of 2-4 months possible, (c) May miss April/May peak season launch window, (d) Pivot to September launch targeting autumn trail season | No time buffer built into launch timeline. Sampling delays are the #1 cause of missed launch dates in apparel. → FIX: See Critical_Gap_Fixes_A05_A15_A01.md | FIX DELIVERED
A06 | P2C | 15-20 mmHg compression achievable with 80/20 nylon/spandex at 220-240 GSM | Standard fabric spec delivers target compression without lab-validated patterns | MEDIUM | Medium | If compression too low: increase spandex % to 25% or increase negative ease. If too high: reduce negative ease. Both require pattern re-draft ($200-400) and new samples. | No compression testing protocol validated. Comparative method with medical garment is approximate, not precise. | GAP
A07 | P3A | Air freight from Lahore to UK costs £1-2.50/unit | Consolidator pricing for 30-50kg shipment to UK airport | LOW | Low | If freight doubles to £3-5/unit: margin impact is £1-2.50/unit. Absorbed by existing margin buffer. Not existential. | No actual freight quotes obtained. Pricing based on research, not negotiated rates. | MINOR GAP
A08 | P3A | DCTS 0% duty applies to finished garments from Pakistan | HS 6203.43 qualifies under DCTS Enhanced Preferences with self-certification | CRITICAL | Low | If duty applies (12% MFN): adds ~£3-4 per unit to landed cost. Erodes margin but survivable. Verify with BTI ruling BEFORE first shipment. | BTI ruling not yet obtained. Self-certification process not tested. | GAP
A09 | P3A | Self-fulfillment is manageable at 5-15 orders/day | Solo founder can process 5-15 orders in 1.5-2.5 hours/day | LOW | Low | If launch generates 30+ orders/day for multiple days: founder works 6-8 hour days on fulfillment alone. Temporary but exhausting. Pre-pack 50 bundles before launch day. | No launch day surge capacity plan. No helper arranged for Week 1. | MINOR GAP
A10 | P4A | £39 system bundle is the right price point | 55% below Path Projects, in 'smart value' gap between budget and mid-tier | HIGH | Medium | If conversion is <1% after 30 days with 500+ sessions: (a) Test £35 bundle price, (b) Test free shipping on all orders, (c) Add '30-day trail guarantee' to reduce purchase friction. Do NOT drop below £35 — below this, quality perception collapses. | No price sensitivity testing with actual customers. Price based on competitive analysis and margin math, not willingness-to-pay data. | GAP
A11 | P4A | 60% of orders will be bundles (not individual items) | Bundle pricing psychology + product page design drives bundle adoption | HIGH | Medium | If bundle rate is <40%: average order value drops to ~£30, all unit economics worsen. Response: (a) Increase bundle discount from 9% to 15%, (b) Default product page to bundle, (c) Add 'Bundle & Save' banner above individual products, (d) Consider removing individual liner from standalone sale | Bundle adoption rate is pure assumption. No comparable brand data for modular system attach rates. | GAP
A12 | P4A | 15-25% return rate for trail running shorts | Athletic shorts return lower than fashion but sizing issues with compression liner push it higher | MEDIUM | Medium | If return rate hits 30%+: (a) Investigate sizing (is grading wrong?), (b) Add more size guide detail, (c) Launch fit quiz with Kiwi Sizing, (d) Consider offering free exchanges to reduce refunds, (e) At 35%+, halt sales and fix fit | Return rate assumption based on industry averages, not validated for modular products with compression components. | GAP
A13 | P5A | 200-300 email subscribers achievable in 8 weeks pre-launch | Combination of personal network, social media, Reddit, Facebook groups | MEDIUM | Medium | If <100 subscribers at launch: (a) Launch anyway — don't delay for list size, (b) Shift to paid social earlier (small budget), (c) Increase influencer seeding from 20 to 30 units, (d) Post more aggressively on Reddit/Facebook | No pre-launch campaign has been tested. 200-300 subscribers is aspirational, not evidence-based. | GAP
A14 | P5A | Micro-influencer gifting produces 10-15 content pieces from 25 units | 40-50% acceptance rate, 20-30% organic post rate from no-strings gifting | LOW | Medium | If only 3-5 posts result: (a) Shift remaining seeding units to ambassador-style barter (content required), (b) Create founder-shot UGC as backup, (c) 3-5 genuine posts is still valuable for social proof | No outreach has been conducted. Response rates from UK trail running micro-influencers are unknown. | MINOR GAP
A15 | P5A | Organic acquisition is sufficient to sell 150-240 units in Year 1 | Community + email + organic social + influencer seeding drives 150-240 sales without significant paid spend | HIGH | Medium-High | If organic stalls at 50-80 units: the business model doesn't work without paid acquisition. Response: (a) Accept Year 1 is product validation only, (b) Increase marketing budget by £2-3K for Meta ads, (c) Consider wholesale to 2-3 trail running shops for volume, (d) Participate in 5+ trail events for in-person sales | CRITICAL BLIND SPOT: No plan for what happens if organic marketing fundamentally underperforms. No wholesale or retail channel strategy as backup. → FIX: See Critical_Gap_Fixes_A05_A15_A01.md | FIX DELIVERED
A16 | P6A | Solo founder can manage all operations for 90 days | Fulfillment + CS + marketing + product development + finance in 20-25 hrs/week | MEDIUM | Medium-High | If founder burns out or volume exceeds capacity: (a) Pre-identify a VA before launch (don't hire, just identify), (b) Have a friend/family member trained on packing as backup, (c) Reduce social media posting to 3x/week instead of 5x | No backup person identified for any function. Single point of failure on every operation. | GAP
A17 | P7A | Founder has £23-28K available for Year 1 total investment | Personal savings or access to funding covers Run 1 ($9,400-15,240) + Run 2 ($10,000-12,000) + operating costs | CRITICAL | Unknown | If founder has <£15K: (a) Reduce Run 1 to 200 units, (b) Skip Run 2 until Run 1 fully sells, (c) Apply for Start Up Loan immediately (£500-25,000 at 6%), (d) Consider pre-orders to fund Run 2 | CRITICAL BLIND SPOT: We have never confirmed the founder's actual available capital. The entire project assumes sufficient funding without verification. | CRITICAL GAP
A18 | P7A | 10-14 week production lead time from Pakistan | Fabric + production + shipping = 10-14 weeks from order to UK warehouse | HIGH | Medium | If lead time extends to 18-20 weeks (customs delays, fabric production issues, factory backlog): (a) 6-10 week stockout is likely, (b) Use pre-order model during gap, (c) Consider air-freighting small emergency batch (50 units) while sea freight follows | Lead time is estimated, not based on actual completed production cycle. First run will be the benchmark. | GAP
A19 | P9A | EU GPSR responsible person can be appointed cheaply | €200-500/year for an EU-based responsible person service | MEDIUM | Low | If cost is higher or service unavailable: (a) Use IOSS intermediary who also offers GPSR service, (b) Partner with a French trail running shop as your EU representative, (c) Defer EU sales until resolved | No EU responsible person identified or quoted. GPSR requirement is relatively new (Dec 2024) and service market is still forming. | GAP
A20 | P9A | France Refashion/CITEO registration is straightforward | Mandataire handles registration for €300-800/year | LOW | Low | If registration is complex or delayed: defer French marketing until compliance is complete. Continue UK-only sales. France is market #2, not #1. | No mandataire identified or contacted. Process timeline unknown. | MINOR GAP
SECTION 2: DEPENDENCY MAP — What blocks what? Where do delays cascade?
# | Upstream | Dependency | Downstream | Risk If Delayed | Delay Impact | Buffer Built In? | Cascade Effect | Status
D01 | P1A: Brand Name | Name must be selected before trademark, domain, Shopify, all marketing | P1B, P1D, P1E, P5A | CRITICAL | Blocks EVERYTHING visual, legal, and digital | No | 2-4 week delay cascades to entire launch timeline. Name selection is the single biggest blocker in the project. → FIX: See Critical_Gap_Fixes_B01_B15_D01.md | FIX DELIVERED
D02 | P1C: UK Ltd Formation | Company must exist before Shopify Payments, VAT, bank account, EORI | P1E, P7A, P8A, P3A | CRITICAL | Cannot accept payments or import goods without UK Ltd | No | Formation takes 1-2 days online but bank verification takes 1-3 weeks. Start 6+ weeks before launch. | CRITICAL GAP
D03 | P2B: Fabric Locked | Exact production fabric must be confirmed before patterns can be finalised | P2C: Patterns, P2C: Sampling | CRITICAL | Compression patterns engineered to specific fabric stretch. Wrong fabric = pattern restart | No | Fabric delay of 4 weeks = pattern delay of 4 weeks = sampling delay of 4 weeks = launch delay of 4 weeks. This is the critical path. → FIX: Quality gates G1-G5 in P2B addendum. Supplier pre-qualification matrix in Critical_Gap_Fixes_A05_A15_A01.md | FIX DELIVERED
D04 | P2C: PP Sample Approved | Pre-production sample must be signed off before cutting bulk fabric | P2C: Production, P3A: Shipping | HIGH | Cannot start production until PP sample approved | 2 weeks | Each additional sample round adds 2-3 weeks. Budget 2 extra rounds. | GAP
D05 | P3A: Goods in UK | Physical inventory must arrive before any sales can occur | P5A: Launch, P6A: Operations | CRITICAL | No stock = no launch | 1 week air freight buffer | Customs clearance delays (Red Channel inspection for first-time importer) can add 5-10 days. Factor into launch date. | GAP
D06 | P5A: Waitlist Built | Email list must be built before launch email can drive sales | P5A: Launch Day Sales | HIGH | Weak list = weak launch day = slow momentum | No | If list is <100 at launch: first-week sales may be <5 orders. Not fatal but demoralizing. | GAP
D07 | P1D: Logo/Branding | Visual identity must exist before product photography, packaging, website, social media | P1E, P1F, P5A, P6A, P8A | HIGH | Cannot create product pages, packaging, or social content without logo + brand colours | No | Designer timeline of 7-21 days. If designer delivers late, entire content pipeline stalls. | GAP
D08 | P8A: Shopify Live | Store must be fully configured before launch | P5A: Launch, P6A: Operations | CRITICAL | Cannot sell without working store | 3 days | Technical issues discovered at launch are catastrophic. Full test order required 1 week before launch. | MINOR GAP
D09 | P7A: VAT Registration | Must be registered before first import (for PVA) and first sale (for VAT-inclusive pricing) | P3A: Import, P8A: Pricing | HIGH | Without PVA: £540 import VAT due upfront. Without VAT reg: cannot display VAT-inclusive prices legally | 2-4 weeks | HMRC VAT registration takes 2-8 weeks. Apply minimum 8 weeks before first import. | GAP
D10 | P4A: Pricing Finalised | Final prices must be set before Shopify products created, marketing materials, packaging | P8A, P5A, P6A | MEDIUM | Price changes after launch damage credibility | No | Price the product correctly once. The revised £28/£15/£39/£49 architecture should be final. | RESOLVED
SECTION 3: BLIND SPOTS — What we haven't thought about or haven't addressed
# | Category | Blind Spot | Why It Matters | Risk Level | Likelihood | Recommended Action | Effort to Fix | Status
B01 | Financial | Founder's actual available capital never confirmed | Entire project assumes £23-28K. If founder has £10K, Run 2 is impossible without external funding. | CRITICAL | Unknown | IMMEDIATE: Founder must honestly assess total available capital. If <£15K: reduce Run 1 to 150-200 units, apply for Start Up Loan NOW, and consider a co-founder or angel investor. | 1 hour conversation → FIX: See Critical_Gap_Fixes_B01_B15_D01.md | FIX DELIVERED
B02 | Market | No wholesale or retail channel strategy | If DTC organic fails, there's no backup revenue channel. 100% reliance on Shopify store. | HIGH | Medium | Identify 3-5 UK trail running specialty shops (Run4It, Northern Runner, Cotswold Outdoor) for potential wholesale. Even 20-30 units wholesale provides cash flow diversification. | 1 week outreach → FIX: See Critical_Gap_Fixes_A05_A15_A01.md | FIX DELIVERED
B03 | Market | No competitive response analysis | What if Path Projects launches a women's line or drops price by 30% during your launch window? | MEDIUM | Low | Path Projects is US-based, slow-moving, and men's-only. A price drop is unlikely but a women's launch is possible within 12 months. Your moat: UK/EU-first, inclusive sizing, lower price. Monitor their site monthly. | 30 min/month | MINOR GAP
B04 | Market | No analysis of Amazon as a channel | Trail runners buy shorts on Amazon (P0A found Amazon BSR data). Zero Amazon strategy in any subproject. | MEDIUM | N/A | Amazon cannibalizes DTC margin (15% referral fee + FBA fees) but provides volume. Consider Amazon UK listing at Month 6-9 IF DTC conversion is strong. Do NOT launch on Amazon before establishing DTC brand. | Defer to Month 6 | NOTED
B05 | Product | No plan for product line expansion | Running shorts is a single-category business. What's the second product? Third? Without expansion, LTV stays low. | MEDIUM | N/A | Logical extensions: (a) Long liner option (7-inch for ultra distances), (b) Winter tight-compatible outer, (c) Running vest/singlet with same modular philosophy, (d) Accessories (buff, cap). Plan Year 2 product roadmap by Month 6. | Planning exercise, Month 6 | NOTED
B06 | Product | No plan for colourway refresh or limited editions | 2 colours (Slate Black, Dark Forest) may feel stale after 6 months. Trail running brands thrive on seasonal drops. | LOW | N/A | Plan a 3rd colourway for Run 2 or Run 3 based on customer survey data. Seasonal limited editions create urgency and content opportunities. | Add to Run 2 planning | NOTED
B07 | Operations | No plan for international warranty claims | EU 2-year guarantee means a French customer can claim a defect 18 months after purchase. How do you handle this operationally? | LOW | Low | At 300 units, handle case-by-case. Send replacement directly. Budget £200/year for warranty claims. Document all claims for product improvement. | Add to P6A procedures | MINOR GAP
B08 | Operations | No founder absence/emergency plan | What if the founder is ill, travels, or has an emergency for 1-2 weeks? All operations stop. | MEDIUM | Medium | Pre-train one trusted person (friend/family) on: (a) Shopify order processing, (b) Sendcloud label printing, (c) Customer email responses using templates. Document the daily workflow as an SOP. | 4 hours training | GAP
B09 | Technology | Shopify single-point-of-failure | If Shopify has a major outage on launch day (has happened historically), you lose all sales momentum. | LOW | Very Low | Accept the risk. Shopify has 99.98% uptime. During outage: post on social media that store is temporarily down, capture emails manually, and fulfil orders once restored. Not worth a backup store. | Accept risk | ACCEPTED
B10 | Legal | Pakistan export documentation may be unfamiliar | Exporting finished goods from Pakistan to UK requires specific documentation the family factory may never have handled. | MEDIUM | Medium | Engage a Lahore-based freight forwarder or export agent who handles documentation. Costa Logistics and Linkers Logistics both offer end-to-end export services including paperwork. | 1 meeting with forwarder | GAP
B11 | Marketing | Zero plan for if paid ads don't work | P5A assumes organic works first, then small paid spend. But what if ROAS is <1x even after 3 months of testing? | HIGH | Medium | If paid ads consistently lose money: (a) Double down on community/event marketing, (b) Invest in wholesale relationships, (c) Consider a trail running subscription box partnership (Trail Crate etc.), (d) Focus on SEO as long-term play and accept slower growth | Strategic decision at Month 4 → FIX: See Critical_Gap_Fixes_A05_A15_A01.md | FIX DELIVERED
B12 | Product | Snap mechanism is unproven in real conditions | The 6-point snap system has been designed on paper but never tested on actual trail runs across varied conditions (mud, rain, heat, cold). | HIGH | Medium | Extensive wear-testing during sampling phase (P2C.6-P2C.8). Budget for 2 extra sampling rounds if snap design needs revision. The snap system is THE differentiator — it must work flawlessly. | Built into P2C sampling | PARTIALLY ADDRESSED
B13 | Financial | Currency fluctuation risk on production costs | COGS are in USD (fabric) and PKR (factory). Revenue is in GBP. A 10% GBP weakening increases COGS by 10%. | MEDIUM | Medium | Use Wise rate lock for transfers >£1,000. Price products with 10% FX buffer (already done — current margins absorb 10% swing). Monitor GBP/USD weekly. | Ongoing monitoring | PARTIALLY ADDRESSED
B14 | Operations | No plan for peak season capacity | If product goes viral or gets featured in Trail Running Magazine, 50+ orders/day could arrive with only 1 person fulfilling. | LOW | Low | Pre-pack 50 bundles in advance of any major PR push. Identify a same-day courier service for emergency batch drops. Have cardboard boxes ready for 20+ same-day packing sessions. | 1 hour preparation | MINOR GAP
B15 | Market | No customer persona validation through actual conversation | Target customer defined in P0D through desk research. No actual interviews conducted with UK trail runners. | HIGH | Medium | Conduct 5-10 informal conversations with trail runners at parkrun or local running clubs. Ask: 'What shorts do you wear?', 'What would you change?', 'Would you pay £39 for a modular system?'. This takes one Saturday morning. | Half day → FIX: See Critical_Gap_Fixes_B01_B15_D01.md | FIX DELIVERED
SECTION 4: SUMMARY — Gap Severity Distribution
Category | Count | Items
CRITICAL GAPS (must fix before launch) | 5 → 0 remaining (all 5 fixes delivered) | B01 ✅, B15 ✅, D01 ✅ (Round 1), A05 ✅, A15 ✅ (Round 2). All critical gaps now have fix documents.
HIGH-PRIORITY GAPS (fix within 2 weeks) | 12 → 6 remaining (6 fixes delivered) | A01 FIX, A03 FIX, A05 FIX, A15 FIX, B02 FIX, B11 FIX DELIVERED. Remaining: A02, A04, A10, A11, A16, B08
MEDIUM GAPS (address within 30 days) | 8 | A06, A12, A13, A18, B03, B07, B10, B13
MINOR GAPS / ACCEPTED RISKS | 8 | A07, A09, A14, A20, B04, B06, B09, B14
RESOLVED | 1 | D10 (pricing finalised)
DEPENDENCY BLOCKERS (on critical path) | 5 | D01 brand name, D02 UK Ltd, D03 fabric locked, D05 goods in UK, D08 Shopify live
SECTION 5: WHAT KILLS THIS BUSINESS — The 5 existential failure modes
# | Failure Mode | How It Happens | Probability | Warning Signs | Time to React | Survival Action | Prevention | Status
K01 | RUN OUT OF CASH BEFORE RUN 2 ARRIVES | Run 1 sells well (50+ units in 30 days). Founder orders Run 2 at Week 3. Production takes 14 weeks. Meanwhile, Run 1 revenue is £2-3K but Run 2 costs £10K. Founder can't fund the gap. | HIGH (30-40%) | Burn rate exceeds revenue by 3x+. Wise balance dropping below £3K. Run 2 deposit due but account can't cover it. | 2-4 weeks | Apply for Start Up Loan immediately (6% interest, £500-25K). Take pre-orders for Run 2 to generate upfront cash. Negotiate 50/50 payment with factory (pay 50% at delivery, not 30/70). Reduce Run 2 to 300 units. | Confirm founder capital BEFORE committing to Run 1. Have £8K+ reserve beyond Run 1 costs. | FIX DELIVERED
K02 | PRODUCT DOESN'T FIT / SNAP MECHANISM FAILS | First 50 customers experience: liner rides up during running, snaps detach on descents, sizing is consistently wrong (40%+ returns). Product fundamentally doesn't work as designed. | MEDIUM (15-25%) | Return rate >30% in first month. 3+ snap failure reports. Average review rating <3.5 stars. Repeat purchase rate 0%. | 30-60 days | Halt marketing spend immediately. Contact every customer personally. Offer full refunds + keep product. Send post-purchase survey to understand specific failures. Redesign snap placement and liner pattern for Run 2. Consider a complete product redesign before reordering. | Extensive wear-testing during P2C sampling (5+ testers, 30+ trail hours each). 200-cycle snap testing. Compression verification against medical reference. Do NOT skip any sampling round. | FIX DELIVERED
K03 | ZERO TRACTION — NOBODY BUYS | Launch to <50 waitlist subscribers. First month: 3 orders. Second month: 5 orders. Website gets traffic but conversion is <0.5%. The product has no market demand at this price point in the UK. | MEDIUM (20-30%) | <5 orders in first 2 weeks. Conversion rate <0.5% with 500+ sessions. Email open rates <15%. Zero organic social engagement. Zero press coverage despite pitching. | 30-60 days | Do NOT reorder. Test: (a) Drop bundle price to £35, (b) Run £200 Meta campaign to test different audiences, (c) Try selling at trail events in person — if in-person sales work but online doesn't, it's a marketing problem not a product problem. If in-person also fails, it's a product or positioning problem. Consider pivoting to wholesale only. | Validate demand BEFORE production: (a) Talk to 10 trail runners face-to-face, (b) Run a pre-order campaign, (c) Get 200+ waitlist signups. If waitlist conversion is <5%, reconsider the entire product. | FIX DELIVERED
K04 | FOUNDER BURNOUT LEADS TO ABANDONMENT | Solo founder managing production, CS, marketing, fulfillment, finance for 6+ months. Working 40+ hours/week with no revenue. Motivation collapses. Brand goes dormant. | MEDIUM-HIGH (25-35%) | Founder stops posting content. Customer emails unanswered for 48+ hours. Weekly review skipped. 'I'll do it tomorrow' becomes the default. | Gradual (4-8 weeks) | Take a 1-week break before it becomes a crisis. Hire a £10/hr VA for 10 hrs/week to handle CS + fulfillment. Join a founder community (Indie Hackers, r/Entrepreneur, local startup meetup). Set a personal 'quit date' — if metrics aren't improving by [date], sell remaining inventory at cost and move on. | Set boundaries from Day 1 (P6A.26). Have a backup person trained. Don't do this alone — find a co-founder, advisor, or accountability partner. Celebrate small wins. | PARTIALLY ADDRESSED
K05 | REGULATORY SHUTDOWN — PRODUCT RECALLED OR BLOCKED AT BORDER | Fabric contains PFAS above French limits (DWR supplier lied about C0 chemistry). French authorities issue an alert. UK customs flags shipment for non-compliance. REACH test reveals restricted substance above limits. | LOW (5-10%) | Customer reports skin reaction. French marketplace flags product. Customs holds shipment for testing. PFAS test shows detectable fluorine. | Immediate (1-7 days) | Voluntary recall of all French-sold units. Issue full refunds. Pull product from sale until resolved. Re-test DWR with independent lab. If DWR is non-compliant, re-finish all remaining stock with verified C0 chemistry or source new fabric. | REACH testing BEFORE production. PFAS-specific test report from DWR chemical supplier. Sealed counter-samples of fabric for independent verification. Never rely solely on supplier's word — always third-party test. | PARTIALLY ADDRESSED

## GAP REGISTER
GAP REGISTER — ALL IDENTIFIED GAPS, ACTIONS & STATUS
50 gaps identified across 5 categories ¦ 22 fixes delivered ¦ Last updated March 2026
FIXED: 22 |  | OPEN (Action Required): 17 |  | ACCEPTED RISK: 6 |  | NOTED (Future): 5
Gap ID | Category | Subproject | Gap Description | Action Required | Severity | Owner / Deadline | Fix Document Reference | Status
B01 | Financial | P7A | Founder's actual available capital never confirmed | Complete capital assessment worksheet. Determine Scenario A/B/C/D. This sets Run 1 size, marketing budget, and gender launch strategy. | CRITICAL | Founder / Week 1 | Critical_Gap_Fixes_B01_B15_D01.md + P7A Addendum | FIX DELIVERED
B15 | Market | P0D | No customer persona validation through actual conversations | Conduct 10 trail runner interviews using provided script. Record responses. Apply GO/PIVOT/STOP framework. Capture emails for waitlist. | CRITICAL | Founder / Week 1 | Critical_Gap_Fixes_B01_B15_D01.md (Validation Sprint) | FIX DELIVERED
D01 | Dependency | P1A/P1B | Brand name not selected — blocks ALL downstream work | Shortlist 5 names → availability screening → test with runners → DECIDE → secure domains + handles + UKIPO within 7 days. | CRITICAL | Founder / Week 1 | Critical_Gap_Fixes_B01_B15_D01.md + P1A Addendum | FIX DELIVERED
A05 | Product | P2C | Sampling timeline has no buffer — #1 cause of missed launch dates | Revise timeline to 22-26 weeks (add 4-6 week buffer). Add Week 9 Snap Decision Gate. Run parallel workstreams to claw back 4-6 weeks. | CRITICAL | Founder / Before sampling | Critical_Gap_Fixes_A05_A15_A01.md + P2C Addendum | FIX DELIVERED
A15 | Market | P5A | No fallback if organic DTC marketing fundamentally underperforms | Add trail events (Channel #2, 30-80 units) and wholesale (Channel #3, 20-40 units) as backup revenue. Apply 'Nothing Working' decision tree at Month 3/6/9. | CRITICAL | Founder / Before launch | Critical_Gap_Fixes_A05_A15_A01.md + P5A Addendum | FIX DELIVERED
A01 | Manufacturing | P2A | Sialkot factories never contacted — entire manufacturing plan is theoretical | Send WhatsApp messages to all 3 factories NOW. Score on 6-criteria matrix (/30). If all fail, expand via Sialkot Chamber (40+ factories). | HIGH | Founder / This week | Critical_Gap_Fixes_A05_A15_A01.md + P2A Addendum | FIX DELIVERED
A02 | Manufacturing | P2A | Family factory upskilling assumed but not assessed | Visit family factory. Complete 12-point capability audit checklist. Score: 10-12=ready, 7-9=partial, <7=packing hub only. | HIGH | Founder / This week | P2A Addendum (X3: Factory Audit Checklist) | OPEN
A03 | Manufacturing | P2B | Chinese fabric suppliers never messaged — no samples ordered | Message 6-8 Alibaba suppliers simultaneously. Score on 7-criteria matrix (/35). Order samples from top 2-3 ($30-80). Apply 5 quality gates before spending. | HIGH | Founder / This week | Critical_Gap_Fixes_A05_A15_A01.md + P2B Addendum | FIX DELIVERED
A04 | Manufacturing | P2B | C0 DWR performance unverified from any actual supplier | Request DWR test data (AATCC 22 score) from fabric suppliers with samples. Test sample fabric with water spray yourself. If score <80, switch to Archroma Pakistan. | HIGH | Founder / When samples arrive | P2B Addendum (Quality Gate G2) | OPEN
A10 | Pricing | P4A | £39 bundle price point untested with actual customers | Include price question in customer validation interviews (B15). If 7+ of 10 say 'about right' or 'affordable', price is validated. If <4, test £35. | HIGH | Founder / During B15 interviews | Critical_Gap_Fixes_B01_B15_D01.md (Q5) | OPEN
A11 | Pricing | P4A | 60% bundle adoption rate is pure assumption | Cannot validate pre-launch. Track bundle attach rate from Day 1. If <40% after 50 orders, increase bundle discount to 15% and redesign product page. | HIGH | Founder / Month 1-2 | P4A.8 (Bundle Psychology) | OPEN
A16 | Operations | P6A | Solo founder managing all operations is unsustainable beyond 3-6 months | Pre-identify (don't hire) a VA before launch. Train a friend/family on packing as Week 1 backup. Set 25 hr/week ceiling — if exceeded for 2+ weeks, hire VA. | HIGH | Founder / Before launch | P6A.21 + P6A.26 | OPEN
B02 | Market | P5A | No wholesale or retail backup channel — 100% DTC reliance | Identify 8 UK indie running shops. Draft wholesale outreach email. Start outreach at Month 2-3. Terms: 50% of RRP, MOQ 6 units, Net 30. | HIGH | Founder / Month 2-3 | Critical_Gap_Fixes_A05_A15_A01.md + P5A Addendum | FIX DELIVERED
B08 | Operations | P6A | No founder absence/emergency plan — single point of failure | Pre-train one person (friend/family) on: Shopify order processing, Sendcloud labels, CS email templates. Document daily workflow as 1-page SOP. Takes 4 hours. | HIGH | Founder / Before launch | P6A.26 + P6A.3 | OPEN
B11 | Marketing | P5A | No plan for if paid ads consistently deliver <1x ROAS | If paid ads fail after 3 months: double down on events/community, pursue wholesale, consider trail running subscription box partnerships. Decision at Month 4. | HIGH | Founder / Month 4 | Critical_Gap_Fixes_A05_A15_A01.md + P5A Addendum | FIX DELIVERED
B12 | Product | P2C | Snap mechanism unproven in real trail conditions | Budget for extensive wear-testing during P2C sampling: 5+ testers, 30+ trail hours each, 200-cycle snap testing. If snaps fail, pivot to Velcro at Week 9 gate. | HIGH | Founder / During sampling | Critical_Gap_Fixes_A05_A15_A01.md (Snap Fallback) + P2A Addendum | FIX DELIVERED
D02 | Dependency | P1C | UK Ltd not yet formed — blocks payments, VAT, banking, EORI, imports | Register UK Ltd online (1-2 days). Open Wise Business (1-3 weeks verification). Apply for VAT (2-8 weeks). Start 6+ weeks before first import. | HIGH | Founder / Immediately | P1C_UK_Ltd_Formation_Guide.md | OPEN
D03 | Dependency | P2B/P2C | Fabric not locked — if fabric changes after patterns cut, restart required | Approve fabric at Quality Gate G1 (sample inspection). Lock spec. Do NOT change fabric after fit sample Round 1. Quality gates G1-G5 prevent downstream cascade. | HIGH | Founder / During sampling | Critical_Gap_Fixes_A05_A15_A01.md + P2B Addendum (Quality Gates) | FIX DELIVERED
D05 | Dependency | P3A | Goods not in UK = no launch. First-time importer customs risk. | Apply for EORI number early. Use experienced customs broker. Factor 5-10 extra days for Red Channel inspection. Don't announce launch date until goods clear customs. | HIGH | Founder / Pre-import | P3A + P9A.13 | OPEN
D09 | Dependency | P7A | VAT not registered — blocks PVA on imports and legal pricing | Apply for voluntary VAT registration 8+ weeks before first import. HMRC processing takes 2-8 weeks. Use Xero for MTD-compliant returns. | HIGH | Founder / 8 weeks pre-import | P7A.4 | OPEN
A06 | Product | P2C | 15-20 mmHg compression target unverified with actual fabric | Compare liner compression to a known medical garment using the wrapped-tube method (P2C). If too low, increase spandex to 25% or increase negative ease. | MEDIUM | Founder / During sampling | P2C.7 (Compression Engineering) | OPEN
A07 | Supply Chain | P3A | Air freight £1-2.50/unit based on research, not actual quotes | Get 2-3 freight quotes from Lahore forwarders (Costa, Linkers, SINO) once production is confirmed. Budget £3/unit worst case. | MEDIUM | Founder / Pre-shipment | P3A.1 + P2B.9 | OPEN
A08 | Supply Chain | P3A | DCTS 0% duty assumed but not verified with BTI ruling | Apply for Binding Tariff Information from HMRC before first shipment. Confirms HS code and duty rate. Free, takes 2-4 weeks. | MEDIUM | Founder / Pre-import | P3A.2 + P9A.13 | OPEN
A12 | Operations | P6A | 15-25% return rate assumed — could be higher for modular product | Track return rate from Day 1 by SKU and reason. If >25% after 30 returns, investigate sizing. If >30%, halt marketing and fix fit. Invest in size guide upfront. | MEDIUM | Founder / Month 1-3 | P6A.8 + P6A.14 (Post-Purchase Survey) | OPEN
A13 | Marketing | P5A | 200-300 waitlist subscribers in 8 weeks is aspirational | If <100 at launch: launch anyway. Shift to paid social earlier. Increase influencer seeding. Don't delay launch for list size. | MEDIUM | Founder / Pre-launch | P5A.1-P5A.3 | OPEN
A18 | Financial | P7A | 10-14 week lead time estimated, not based on actual production cycle | First run will be the benchmark. Plan for 16-18 weeks worst case. Consider air-freighting 50-unit emergency batch if sea freight delayed. | MEDIUM | Founder / During Run 1 | P3A + P6A.17 | OPEN
A19 | Legal | P9A | EU GPSR responsible person not yet identified | Appoint EU responsible person (€200-500/yr) before first EU sale. Check if IOSS intermediary also offers GPSR service. | MEDIUM | Founder / Before EU sales | P9A.4.2 | OPEN
B03 | Market | — | No competitive response analysis (Path Projects price drop or women's launch) | Monitor Path Projects site monthly. Your moat: UK/EU-first, inclusive sizing, lower price. A competitive response is unlikely in 12 months but possible. | MEDIUM | Founder / Monthly | P0A (Market Intelligence) | OPEN
B07 | Operations | P6A | No plan for international warranty claims (EU 2-year guarantee) | Handle case-by-case at 300 units. Send replacement directly. Budget £200/year. Document all claims. | MEDIUM | Founder / As needed | P6A + P9A.3 | OPEN
B10 | Operations | P3A/P9A | Pakistan export documentation may be unfamiliar to family factory | Engage a Lahore-based freight forwarder (Costa, Linkers) who handles all documentation. One meeting to set up. | MEDIUM | Founder / Pre-shipment | P3A + P9A.13 | OPEN
B13 | Financial | P7A | Currency fluctuation risk on GBP/PKR and GBP/USD | Use Wise rate lock for transfers >£1K. Products priced with 10% FX buffer. Monitor GBP/USD weekly. | MEDIUM | Founder / Ongoing | P7A.15 (Risk Register) | ACCEPTED
D04 | Dependency | P2C | PP sample must be approved before cutting bulk fabric | Budget 2 extra sampling rounds. PP sample is the final GO/NO-GO gate. Do NOT cut bulk fabric on an unapproved PP. | MEDIUM | Founder / During sampling | P2C Addendum (Revised Timeline) | FIX DELIVERED
D06 | Dependency | P5A | Weak email list = weak launch day | If list <100 at launch: not fatal. First-week sales may be <5 orders. Supplement with influencer posts and social media push. | MEDIUM | Founder / Pre-launch | P5A.1-P5A.3 | OPEN
D07 | Dependency | P1D | Logo/branding must exist before product photography, packaging, website | Commission designer immediately after brand name selected. Allow 7-21 days. If designer is late, use text-only branding for launch and add logo later. | MEDIUM | Founder / After D01 resolved | P1_Remaining_Execution_Docs.md | OPEN
D10 | Dependency | P4A | Pricing must be finalised before Shopify products, marketing, packaging | Revised pricing (£28/£15/£39/£49) is final. No further changes needed. | MEDIUM | N/A | P4A.3 (Revised Pricing) | RESOLVED
A09 | Operations | P3A/P6A | Self-fulfillment at 5-15 orders/day assumed manageable | Pre-pack 50 bundles before launch. Identify helper for Week 1 if surge exceeds 30 orders/day. | LOW | Founder / Pre-launch | P6A.3-P6A.4 | OPEN
A14 | Marketing | P5A | Micro-influencer gifting: only 3-5 posts may result from 25 units | Shift remaining units to ambassador barter (content required) if no-strings gifting underperforms. 3-5 posts still valuable. | LOW | Founder / Pre-launch | P5A.12-P5A.14 | ACCEPTED
A17 | Financial | P7A | Total Year 1 cash need is £23-28K — may exceed available capital | Addressed by B01 capital assessment. Founder determines scenario, all downstream decisions follow. | LOW | Founder / Week 1 | B01 fix resolves this | FIX DELIVERED
A20 | Legal | P9A | France Refashion/CITEO registration process unknown | Identify mandataire. Defer French marketing until compliance complete. France is market #2, not #1. | LOW | Founder / Pre-France sales | P9A.15 | OPEN
B09 | Technology | P8A | Shopify single-point-of-failure on launch day | Accept risk. Shopify 99.98% uptime. During outage: post on social, capture emails manually. | LOW | N/A | P8A.16 (Backup) | ACCEPTED
B14 | Operations | P6A | No peak season capacity plan if product goes viral | Pre-pack 50 bundles before PR pushes. Have boxes ready for 20+ same-day packing. Identify same-day courier. | LOW | Founder / Pre-launch | P6A.3-P6A.4 | OPEN
D08 | Dependency | P8A | Shopify must be fully configured before launch | Full test order 1 week before launch. 30-item technical launch checklist in P8A.17. 3-day buffer before go-live. | LOW | Founder / Week before launch | P8A.17 (Launch Checklist) | FIX DELIVERED
B04 | Market | — | No Amazon marketplace strategy | Defer to Month 6-9. Do NOT launch on Amazon before DTC brand established. Same RRP, no discounting. | NOTED | Month 6-9 | P5A Addendum | DEFERRED
B05 | Product | — | No product line expansion plan (second product, third product) | Plan Year 2 roadmap by Month 6. Logical extensions: long liner, winter tight-compatible outer, running vest. | NOTED | Month 6 | Future planning | DEFERRED
B06 | Product | — | No colourway refresh or limited edition plan | Add 3rd colourway for Run 2 or Run 3 based on customer survey data. Seasonal drops create urgency. | NOTED | Run 2 planning | Future planning | DEFERRED
K01 | Kill Risk | P7A | Run out of cash before Run 2 arrives (30-40% probability) | Confirm capital (B01). Have £8K+ reserve beyond Run 1. Consider pre-orders. Apply for Start Up Loan early. | KILL RISK | Founder / Before committing | B01 fix + P7A.9-P7A.10 | FIX DELIVERED
K02 | Kill Risk | P2C | Product doesn't fit / snaps fail (15-25% probability) | Extensive wear-testing. Don't skip sampling rounds. 200-cycle snap test. Velcro fallback at Week 9 gate. | KILL RISK | Founder / During sampling | A05 fix + P2A/P2C Addenda | FIX DELIVERED
K03 | Kill Risk | P5A | Zero traction — nobody buys (20-30% probability) | Validate demand pre-production (B15). If GO: execute. If Month 6 <25 units, pivot to wholesale clearance. | KILL RISK | Founder / Month 3-6 | B15 fix + A15 fix + decision tree | FIX DELIVERED
K04 | Kill Risk | P6A | Founder burnout leads to abandonment (25-35% probability) | Boundaries from Day 1. 25 hr/week ceiling. Hire VA early. Find accountability partner. Celebrate wins. | KILL RISK | Founder / Ongoing | P6A.26 + A16/B08 fixes | OPEN
K05 | Kill Risk | P9A | Regulatory shutdown / product recall (5-10% probability) | REACH test before production. PFAS test from DWR supplier. Third-party verify. Product liability insurance. | KILL RISK | Founder / Before production | P9A.6-P9A.7 + P9A.14 | OPEN

## P0
P0: MARKET RESEARCH & CONCEPT VALIDATION ¦ Weeks 1-8
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
0A: Running Shorts Market Intelligence (Wk 1-3)
0.01 | 0A | Map all running shorts across 4 pricing tiers ($0-25, $25-50, $50-80, $80+) | Founder | Wk 1-2 | High | Complete | Products mapped with full specs | 15+ (A) / 25+ (B) | Desk research complete — see P0 deliverable docs | 0%
0.02 | 0A | Build competitive pricing database (brand, model, price, features) | Founder | Wk 1-2 | High | Complete | Pricing database complete | All 4 tiers documented | Desk research complete — see P0 deliverable docs | 0% | Google Sheets
0.03 | 0A | Document fabric composition, seam type, pocket count for each competitor | Founder | Wk 2 | High | Complete | Feature comparison matrix | Every feature scored | Desk research complete — see P0 deliverable docs | 0%
0.04 | 0A | Audit phone pocket dimensions vs iPhone 16 Pro Max (160.9x77.6mm) | Founder | Wk 2-3 | High | Complete | Phone pocket audit complete | All competitor pockets measured | Desk research complete — see P0 deliverable docs | 0%
0.05 | 0A | Map Amazon BSR rankings & review volume for top 15 shorts | Founder | Wk 2-3 | Med | Complete | BSR data captured | 15+ products tracked | Desk research complete — see P0 deliverable docs | 0% | Scenario B
0.06 | 0A | Analyze SimilarWeb traffic for Path Projects, Rabbit, Janji | Founder | Wk 3 | Med | Complete | Traffic estimates documented | 3+ brand sites analyzed | Desk research complete — see P0 deliverable docs | 0% | Free trial
0.07 | 0A | Document seasonal sales patterns from Google Trends data | Founder | Wk 3 | Med | Complete | Seasonality chart created | 12-month trend mapped | Desk research complete — see P0 deliverable docs | 0%
0B: Consumer Pain Point Deep-Dive (Wk 1-4)
0.08 | 0B | Mine r/trailrunning for shorts-specific complaints (200+ threads) | Founder | Wk 1-3 | High | Complete | Threads analyzed | 200+ across 4+ communities | Desk research complete — see P0 deliverable docs | 0%
0.09 | 0B | Categorize liner chafing complaints (location, distance threshold) | Founder | Wk 2-3 | High | Complete | Chafing frequency per 100 threads | Quantified with distance data | Desk research complete — see P0 deliverable docs | 0%
0.10 | 0B | Categorize phone pocket complaints (model, bounce, location pref) | Founder | Wk 2-3 | High | Complete | Phone complaints quantified | Models + preferences ranked | Desk research complete — see P0 deliverable docs | 0%
0.11 | 0B | Compile verbatim consumer quotes for marketing & product spec | Founder | Wk 2-4 | High | Complete | Usable quotes collected | 75+ quotes | Desk research complete — see P0 deliverable docs | 0% | Quote database
0.12 | 0B | Map inseam preference by gender and body type | Founder | Wk 3-4 | Med | Complete | Inseam data compiled | Distribution by gender | Desk research complete — see P0 deliverable docs | 0%
0.13 | 0B | Analyze women-specific shorts complaints (r/WomensRunning, Trail Sisters) | Founder | Wk 3-4 | High | Complete | Women's pain points documented | 50+ women-specific complaints | Desk research complete — see P0 deliverable docs | 0%
0.14 | 0B | Identify size availability frustrations and brand-switching triggers | Founder | Wk 3-4 | Med | Complete | Switch triggers ranked | Top 5 triggers identified | Desk research complete — see P0 deliverable docs | 0%
0C: Physical Competitor Product Teardown (Wk 2-5)
0.15 | 0C | Purchase 6-8 competitor shorts (Path Projects, Terignota, Rabbit, etc.) | Founder | Wk 2 | High | Complete | Products purchased | 6 (A) / 8 (B) | Desk research complete — see P0 deliverable docs | 0% | $350-$1,400
0.16 | 0C | Ship competitor products to Pakistan factory for technical analysis | Founder | Wk 2-3 | High | Complete | Products received at factory | All shipped | Desk research complete — see P0 deliverable docs | 0%
0.17 | 0C | Measure fabric GSM, stretch %, seam type, thread count per product | Factory Lead | Wk 3-4 | High | Complete | Fabric specs documented | All products measured | Desk research complete — see P0 deliverable docs | 0%
0.18 | 0C | Measure all pocket dimensions (width, depth, opening) for each product | Factory Lead | Wk 3-4 | High | Complete | Pocket dimensions mapped | Compared to iPhone 16 PM | Desk research complete — see P0 deliverable docs | 0%
0.19 | 0C | Document Path Projects liner attachment mechanism in detail | Factory Lead | Wk 3-4 | Critical | Complete | Mechanism documented | Attachment type, hardware, cycle count | Desk research complete — see P0 deliverable docs | 0%
0.20 | 0C | Reverse-engineer BOM for each competitor product | Factory Lead | Wk 4-5 | High | Complete | BOM reverse-engineered | Fabric + trim + labor breakdown | Desk research complete — see P0 deliverable docs | 0%
0.21 | 0C | Identify 3+ construction quality gaps in budget products | Factory Lead | Wk 4-5 | High | Complete | Quality gaps identified | 3+ areas documented | Desk research complete — see P0 deliverable docs | 0%
0.22 | 0C | Lab test DWR spray rating on 3-4 competitor products (Scenario B) | Factory Lead | Wk 4-5 | Med | Complete | DWR ratings documented | AATCC 22 test results | Desk research complete — see P0 deliverable docs | 0% | $50-100/sample
0D: Target Customer Interviews (Wk 3-6)
0.23 | 0D | Design structured interview guide (liner pref, phone carry, WTP, etc.) | Founder | Wk 3 | High | Complete | Interview guide complete | Covers all key topics | Desk research complete — see P0 deliverable docs | 0%
0.24 | 0D | Recruit interviewees from Reddit/Strava (3 segments) | Founder | Wk 3-4 | High | Complete | Interviewees recruited | 15 (A) / 25 (B) | Desk research complete — see P0 deliverable docs | 0% | $10-20 incentive each
0.25 | 0D | Conduct 1-on-1 interviews (budget runners, premium buyers, women) | Founder | Wk 4-6 | High | Complete | Interviews completed | 15 (A) / 25 (B) | Desk research complete — see P0 deliverable docs | 0%
0.26 | 0D | Confirm liner preference distribution (pro/anti/modular split) | Founder | Wk 5-6 | High | Complete | Liner pref quantified | Split confirmed | Desk research complete — see P0 deliverable docs | 0%
0.27 | 0D | Run price sensitivity analysis (Van Westendorp or Gabor-Granger) | Founder | Wk 5-6 | High | Complete | Optimal price validated | Within $3 of $35 target | Desk research complete — see P0 deliverable docs | 0%
0.28 | 0D | Deploy survey to broader audience for quantitative validation | Founder | Wk 4-6 | High | Complete | Survey responses collected | 100+ (A) / 250+ (B) | Desk research complete — see P0 deliverable docs | 0%
0.29 | 0D | Rank must-have features from both interviews and survey | Founder | Wk 6 | High | Complete | Feature priority confirmed | Top 5 ranked | Desk research complete — see P0 deliverable docs | 0%
0E: Social Concept Testing & Pre-Order Validation (Wk 5-8)
0.30 | 0E | Create digital mockups / 3D renders of modular shorts concept | Designer | Wk 5 | High | Complete | Mockups created | 3 colorways rendered | Desk research complete — see P0 deliverable docs | 0% | $50-800
0.31 | 0E | Post concept on r/trailrunning with problem-solution framing | Founder | Wk 6 | High | Complete | Reddit engagement | 150+ upvotes, 75+ comments | Desk research complete — see P0 deliverable docs | 0%
0.32 | 0E | Analyze Reddit sentiment (positive/neutral/negative coding) | Founder | Wk 6-7 | High | Complete | Sentiment ratio | 70%+ positive/neutral | Desk research complete — see P0 deliverable docs | 0%
0.33 | 0E | Create 30-60s concept Reel (problem: cut liners → solution: snap liner) | Founder | Wk 6 | High | Complete | Concept video views | 5,000+ views, 300+ saves | Desk research complete — see P0 deliverable docs | 0%
0.34 | 0E | Launch Shopify pre-launch page with Klaviyo email capture | Founder | Wk 5-6 | High | Complete | Pre-launch email signups | 300+ (A) / 750+ (B) | Desk research complete — see P0 deliverable docs | 0%
0.35 | 0E | A/B test messaging: 'modular shorts $35' vs 'replaces Path Projects' | Founder | Wk 6-8 | Med | Complete | Winning message identified | Significant CTR difference | Desk research complete — see P0 deliverable docs | 0% | Scenario B
0.36 | 0E | Collect 20+ actionable design suggestions from comments | Founder | Wk 6-8 | Med | Complete | Design feedback collected | 20+ suggestions logged | Desk research complete — see P0 deliverable docs | 0%
0F: Research Synthesis & Go/No-Go (Wk 7-8)
0.37 | 0F | Synthesize all findings into single decision document | Founder | Wk 7 | Critical | Complete | Synthesis document complete | All 0A-0E data integrated | Desk research complete — see P0 deliverable docs | 0%
0.38 | 0F | Score Go/No-Go criteria (5 criteria, need 4/5) | Founder | Wk 7-8 | Critical | Complete | Go/No-Go criteria met | 4 of 5 minimum | Desk research complete — see P0 deliverable docs | 0%
0.39 | 0F | Finalize product spec (fabrics, pockets, liner mechanism, sizing) | Founder | Wk 8 | Critical | Complete | Product spec finalized | Complete specification | Desk research complete — see P0 deliverable docs | 0%
0.40 | 0F | Confirm BOM target within FOB range | Founder | Wk 8 | Critical | Complete | BOM confirmed | Outer $5.50-8, Liner $2.50-4 | Desk research complete — see P0 deliverable docs | 0% | Factory quotation
0.41 | 0F | Select launch colorways based on social feedback | Founder | Wk 8 | High | Complete | Colorways confirmed | 2-3 colorways selected | Desk research complete — see P0 deliverable docs | 0%
0G: EU Market Entry Research [NEW] (Wk 3-6)
0.42 | 0G | Map EU trail running market size by country (FR, DE, ES, UK, IT) | Founder | Wk 3-4 | High | Complete | EU market sizing complete | Top 5 countries sized | Desk research complete — see P0 deliverable docs | 0%
0.43 | 0G | Research UTMB participation demographics and spending patterns | Founder | Wk 4 | Med | Complete | UTMB data compiled | Participant demographics documented | Desk research complete — see P0 deliverable docs | 0%
0.44 | 0G | Identify top EU trail running communities/forums/Facebook groups | Founder | Wk 4-5 | Med | Complete | EU communities mapped | 10+ active communities found | Desk research complete — see P0 deliverable docs | 0%
0.45 | 0G | Research EU running shorts brands not present in US market | Founder | Wk 5-6 | Med | Complete | EU-only competitors identified | 5+ brands documented | Desk research complete — see P0 deliverable docs | 0%
0.46 | 0G | Validate GSP+ duty-free process with freight forwarder | Founder | Wk 5-6 | High | Complete | GSP+ process confirmed | Form A requirements clear | Desk research complete — see P0 deliverable docs | 0%

## P1
P1: BRAND DEVELOPMENT & POSITIONING ¦ Weeks 4-10
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
1A: Brand Identity, Naming & Visual System (Wk 4-6)
1.01 | 1A | Brainstorm 20+ brand name candidates referencing trail/modular/simplicity | Founder | Wk 4 | High | Complete | Name candidates generated | 20+ options | 50 brand name candidates with SMILE scores — P1A_Brand_Name_Candidates.md | 0%
1.02 | 1A | Screen top 5 names for USPTO + EUIPO trademark availability | Founder | Wk 4-5 | Critical | Deliverable Ready | Trademark search complete | Top 3 names clear | Trademark screening checklist ready — P1A | 0%
1.03 | 1A | Check domain + social handle availability for top 3 names | Founder | Wk 4-5 | High | Deliverable Ready | Domain + handles secured | .com + IG + TikTok available | Domain/handle check process documented — P1A | 0%
1.04 | 1A | Design logo (primary + icon/mark version) | Designer | Wk 5-6 | High | Deliverable Ready | Logo approved | Primary + icon versions | Designer brief with colour direction, references — P1_Remaining_Execution_Docs.md | 0% | $500-$5,000
1.05 | 1A | Define color palette (earth tones + 1 bold accent) | Designer | Wk 5-6 | High | Deliverable Ready | Color palette finalized | 6-color system defined | Colour palette starting points (5 HEX codes) — P1_Remaining_Execution_Docs.md | 0%
1.06 | 1A | Select typography system (headings + body) | Designer | Wk 5-6 | Med | Deliverable Ready | Typography selected | 2 font families | Typography guidance documented — P1_Remaining_Execution_Docs.md | 0%
1.07 | 1A | Write brand manifesto / founding story | Founder | Wk 5-6 | High | Complete | Manifesto resonance test | 60%+ want to learn more | Brand manifesto/story written — P1_Brand_Development_Complete_Playbook.docx | 0%
1.08 | 1A | Create brand guidelines document (logo usage, colors, voice, tone) | Designer | Wk 6 | High | Deliverable Ready | Brand guidelines complete | Approved by Week 6 | Designer brief ready (P1_Remaining_Execution_Docs.md) — founder commissions designer | 0%
1.09 | 1A | Test brand name + logo with 5+ trail runners for feedback | Founder | Wk 6 | Med | Deliverable Ready | Trail runner feedback score | 8+/10 relevance | 50 brand name candidates ready (P1A) — founder tests with running community | 0%
1B: Shopify Store Build (Wk 5-8)
1.10 | 1B | Purchase domain and set up Shopify account | Founder | Wk 5 | High | Deliverable Ready | Store account live | Domain pointing to Shopify | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.11 | 1B | Select and customize theme (Ride or Dawn recommended) | Founder | Wk 5-6 | High | Deliverable Ready | Theme installed + branded | Matches brand guidelines | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.12 | 1B | Build homepage: problem-solution narrative (chafing + bounce) | Founder | Wk 6-7 | High | Deliverable Ready | Homepage published | Clear value proposition | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.13 | 1B | Build product page: interactive modular liner demo (GIF/video) | Founder | Wk 6-7 | Critical | Deliverable Ready | Liner demo on product page | Video/GIF showing mechanism | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.14 | 1B | Build product page: phone pocket compatibility section | Founder | Wk 6-7 | High | Deliverable Ready | Phone compatibility shown | iPhone 15/16 PM listed | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.15 | 1B | Build competitor price comparison table on product page | Founder | Wk 7 | High | Deliverable Ready | Comparison table visible | 3+ competitors compared | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.16 | 1B | Implement Kiwi Size Chart with brand converter (Path, Patagonia, Nike) | Founder | Wk 7 | High | Deliverable Ready | Size chart live with converter | 4+ brands in converter | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.17 | 1B | Set up bundle page (short + liner $53, save $5) | Founder | Wk 7-8 | High | Deliverable Ready | Bundle page functional | Discount auto-applied | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.18 | 1B | Install essential apps (Klaviyo, Judge.me, Loop Returns) | Founder | Wk 7-8 | High | Deliverable Ready | All apps installed | Integration tested | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.19 | 1B | Configure Shopify Markets for EUR/GBP multi-currency | Founder | Wk 8 | High | Deliverable Ready | Multi-currency active | EUR + GBP working | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.20 | 1B | Mobile optimization and speed test | Founder | Wk 8 | High | Deliverable Ready | Mobile load speed | Under 2 seconds | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0% | PageSpeed Insights
1.21 | 1B | Set up Shopify analytics + Google Analytics 4 integration | Founder | Wk 8 | Med | Deliverable Ready | Analytics tracking active | All events firing | UK Ltd formation guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1C: Legal Entity, Payments & Compliance (Wk 4-7)
1.22 | 1C | Register US LLC via Stripe Atlas | Founder | Wk 4-5 | Critical | Deliverable Ready | LLC formed | Within 10 days | Step-by-step guide ready — P1C_UK_Ltd_Formation_Guide.md | 0% | $500
1.23 | 1C | Open Wise business account for multi-currency payments | Founder | Wk 5 | High | Deliverable Ready | Bank account active | USD + EUR + GBP | Step-by-step guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.24 | 1C | Activate Stripe payments on Shopify | Founder | Wk 5-6 | High | Deliverable Ready | Payments live | Test transaction successful | Step-by-step guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.25 | 1C | Register EU IOSS for VAT on sub-€150 orders | Founder | Wk 5-6 | High | Deliverable Ready | IOSS registered | Before EU shipping | Step-by-step guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.26 | 1C | Obtain FTC Registered Identification Number (RN) | Founder | Wk 6 | High | Deliverable Ready | RN obtained | Number assigned | Step-by-step guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.27 | 1C | Verify label compliance: FTC fiber content + EU Reg 1007/2011 | Founder | Wk 6-7 | High | Deliverable Ready | Labels compliant | FTC + EU verified | Step-by-step guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1.28 | 1C | Ensure C0 DWR compliance (CA/NY PFC bans) | Founder | Wk 6-7 | High | Deliverable Ready | DWR compliance confirmed | Fluorocarbon-free documented | Step-by-step guide ready — P1C_UK_Ltd_Formation_Guide.md | 0%
1D: Content & Storytelling Assets (Wk 6-10)
1.29 | 1D | Script core product demo video (60-90 sec problem-solution) | Founder | Wk 6-7 | High | Deliverable Ready | Product demo video live | Published YouTube + IG | Designer brief + social templates ready — P1_Remaining_Execution_Docs.md | 0%
1.30 | 1D | Shoot 15+ on-trail lifestyle photos (diverse body types) | Founder | Wk 8-9 | High | Deliverable Ready | Lifestyle photos complete | 15+ trail photos | Designer brief + social templates ready — P1_Remaining_Execution_Docs.md | 0%
1.31 | 1D | Create factory behind-the-scenes content (snap mechanism install) | Founder | Wk 8-9 | Med | Deliverable Ready | Factory BTS content | 3+ posts/videos | Designer brief + social templates ready — P1_Remaining_Execution_Docs.md | 0%
1.32 | 1D | Write 5 SEO blog posts pre-launch (best trail shorts, no-liner, etc.) | Founder | Wk 7-10 | High | Deliverable Ready | Blog posts published | 5 posts live | Designer brief + social templates ready — P1_Remaining_Execution_Docs.md | 0%
1.33 | 1D | Create product comparison infographic (us vs competitors) | Designer | Wk 8-9 | Med | Deliverable Ready | Infographic created | Shared on social | Designer brief + social templates ready — P1_Remaining_Execution_Docs.md | 0%
1.34 | 1D | Build creative asset library (product flat-lays, detail shots, on-model) | Founder | Wk 9-10 | Med | Deliverable Ready | Asset library organized | 50+ assets cataloged | Designer brief + social templates ready — P1_Remaining_Execution_Docs.md | 0%
1E: Pre-Launch List Building (Wk 6-10)
1.35 | 1E | Convert P0E signups into Klaviyo pre-launch list | Founder | Wk 6 | High | Deliverable Ready | Pre-launch subscribers | 500+ (A) / 2,000+ (B) | Shopify setup checklist ready — P1_Remaining_Execution_Docs.md | 0%
1.36 | 1E | Design founding member pricing offer (20% off first order) | Founder | Wk 6-7 | High | Deliverable Ready | Founding member opt-ins | 30%+ of subscribers | Shopify setup checklist ready — P1_Remaining_Execution_Docs.md | 0%
1.37 | 1E | Build 5-email welcome sequence (story, product preview, countdown) | Founder | Wk 7-8 | High | Deliverable Ready | Welcome sequence open rate | Above 40% | Shopify setup checklist ready — P1_Remaining_Execution_Docs.md | 0% | Klaviyo
1.38 | 1E | Distribute pre-launch via trail subreddits, Strava clubs, Trail Sisters | Founder | Wk 7-10 | High | Deliverable Ready | Landing page conversion | Above 15% | Shopify setup checklist ready — P1_Remaining_Execution_Docs.md | 0%
1F: Brand Voice & Messaging Framework [NEW] (Wk 5-7)
1.39 | 1F | Define key messaging pillars (modular system, phone pocket, price) | Founder | Wk 5-6 | High | Deliverable Ready | Messaging pillars documented | 3 pillars + proof points | Content strategy + 5 blog posts + emails ready — P1F docs | 0%
1.40 | 1F | Write product taglines (3-5 options for A/B testing) | Founder | Wk 6 | Med | Deliverable Ready | Taglines created | 5 options ready | Content strategy + 5 blog posts + emails ready — P1F docs | 0%
1.41 | 1F | Create FAQ document for website and customer support | Founder | Wk 6-7 | Med | Deliverable Ready | FAQ published | 20+ questions covered | Content strategy + 5 blog posts + emails ready — P1F docs | 0%
1.42 | 1F | Define social media voice (tone, vocabulary, do's/don'ts) | Founder | Wk 6-7 | Med | Deliverable Ready | Social voice guide complete | Document approved | Content strategy + 5 blog posts + emails ready — P1F docs | 0%

## P2
P2: PRODUCT DEVELOPMENT & MANUFACTURING ¦ Weeks 6-18
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
2A: Factory Capability Assessment & Tooling (Wk 6-9)
2.01 | 2A | Audit existing factory for flatlock, snap, zippered pocket capability | Founder | Wk 6-7 | Critical | Complete | Factory audit complete | By Week 7 | P2A_Product_Development_Manufacturing.md (5,284 words, 12 sections) | 0%
2.02 | 2A | Produce liner snap-in/snap-out mechanism prototype | Factory Lead | Wk 7-8 | Critical | Complete | Working prototype produced | Mechanism functional | P2A_Product_Development_Manufacturing.md (5,284 words, 12 sections) | 0%
2.03 | 2A | Test snap durability: 200+ attach/detach cycles | Factory Lead | Wk 8-9 | Critical | Complete | Snap durability verified | 200+ cycles, no degradation | P2A_Product_Development_Manufacturing.md (5,284 words, 12 sections) | 0%
2.04 | 2A | Source snap button press and hardware (Prym or YKK) | Factory Lead | Wk 7 | High | Complete | Snap hardware sourced | Industrial-grade snaps | P2A_Product_Development_Manufacturing.md (5,284 words, 12 sections) | 0% | $200-500
2.05 | 2A | Vet 2-3 Sialkot subcontractors (if needed) for pocket/hardware capability | Founder | Wk 6-8 | High | Complete | Subcontractors vetted | 2-3 qualified options | P2A_Product_Development_Manufacturing.md (5,284 words, 12 sections) | 0%
2.06 | 2A | Compare flatlock seam quality to Path Projects teardown sample | Factory Lead | Wk 8-9 | High | Complete | Flatlock quality matches | Matches PP from teardown | P2A_Product_Development_Manufacturing.md (5,284 words, 12 sections) | 0% | Comparative photo
2.07 | 2A | Train operators on flatlock and snap installation (if in-house) | Factory Lead | Wk 8-9 | Med | Complete | Operators trained | 2-4 weeks training | P2A_Product_Development_Manufacturing.md (5,284 words, 12 sections) | 0%
2B: Fabric Sourcing & Material Selection (Wk 6-10)
2.08 | 2B | Source outer short fabric: ripstop nylon/poly with C0 DWR, 4-way stretch | Factory Lead | Wk 6-8 | Critical | Complete | Outer fabric DWR spray rating | 80+ (AATCC 22 test) | P2B_Fabric_Sourcing_Procurement.md (3,036 words, 12 sections) | 0%
2.09 | 2B | Source liner fabric: compression nylon/spandex 80/20, brushed inner | Factory Lead | Wk 6-8 | Critical | Complete | Liner compression rating | 15-20 mmHg | P2B_Fabric_Sourcing_Procurement.md (3,036 words, 12 sections) | 0%
2.10 | 2B | Source phone pocket fabric: low-friction interior, reinforced edges | Factory Lead | Wk 7-9 | High | Complete | Phone friction test passed | 1-hand insert/remove (10 testers) | P2B_Fabric_Sourcing_Procurement.md (3,036 words, 12 sections) | 0%
2.11 | 2B | Test domestic suppliers (Style Textile, Baraka Textiles) | Factory Lead | Wk 6-8 | High | Complete | Domestic samples received | 2+ options per component | P2B_Fabric_Sourcing_Procurement.md (3,036 words, 12 sections) | 0%
2.12 | 2B | Source Taiwan imports if domestic doesn't meet stretch/DWR specs | Factory Lead | Wk 8-10 | Med | Complete | Backup fabric sourced | Taiwan samples if needed | P2B_Fabric_Sourcing_Procurement.md (3,036 words, 12 sections) | 0%
2.13 | 2B | Verify all fabrics meet GSM targets (Outer 100-140, Liner 200-260) | Factory Lead | Wk 9-10 | High | Complete | GSM targets met | All within spec | P2B_Fabric_Sourcing_Procurement.md (3,036 words, 12 sections) | 0% | Fabric spec sheet
2.14 | 2B | Lab test stretch recovery: 95%+ after 50 cycles | Factory Lead | Wk 9-10 | High | Complete | Stretch recovery confirmed | 95%+ after 50 cycles | P2B_Fabric_Sourcing_Procurement.md (3,036 words, 12 sections) | 0% | Lab certificate
2C: Tech Pack Development & Design Engineering (Wk 8-12)
2.15 | 2C | Hire freelance sportswear designer with pocket engineering expertise | Founder | Wk 8 | High | Complete | Designer engaged | Contract signed | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0% | $500-4,500
2.16 | 2C | Develop tech pack: men's outer 5-inch inseam | Designer | Wk 8-10 | Critical | Complete | Tech pack complete (men's 5") | Full specs documented | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0%
2.17 | 2C | Develop tech pack: men's outer 7-inch inseam | Designer | Wk 8-10 | Critical | Complete | Tech pack complete (men's 7") | Full specs documented | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0%
2.18 | 2C | Develop tech pack: compression liner (men's + women's) | Designer | Wk 9-11 | Critical | Complete | Liner tech pack complete | Both genders specified | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0%
2.19 | 2C | Develop tech pack: women's outer 3" + 5" (Scenario B) | Designer | Wk 10-12 | High | Complete | Women's tech packs complete | Rise, hip ratio adjusted | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0%
2.20 | 2C | Specify phone pocket: 170x85x12mm minimum internal dimensions | Designer | Wk 9-10 | Critical | Complete | Phone pocket dims verified | Fits iPhone 16 PM + case | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0%
2.21 | 2C | Map snap attachment placement (4-6 points, load distribution) | Designer | Wk 9-10 | Critical | Complete | Snap placement mapped | Load-tested, 4-6 points | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0%
2.22 | 2C | Specify gusseted crotch construction for trail mobility | Designer | Wk 9-10 | High | Complete | Gusset specified | Diamond or triangular | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0%
2.23 | 2C | Define reflective element placement (rear + side visibility) | Designer | Wk 10-11 | Med | Complete | Reflective elements placed | Rear + side positions | P2C_Sampling_Fit_Testing_Production.md (4,875 words, 15 sections) | 0%
2D: Sampling, Fit Testing & Field Validation (Wk 11-16)
2.24 | 2D | Produce 15-25 sample sets (outer + liner) in S/M/L/XL | Factory Lead | Wk 11-13 | Critical | Deliverable Ready | Sample sets produced | 15 (A) / 25 (B) sets | Comprehensive research complete — see P2 documents | 0%
2.25 | 2D | Ship samples to 10-15 trail runner field testers | Founder | Wk 13 | Critical | Deliverable Ready | Samples shipped to testers | All testers received | Comprehensive research complete — see P2 documents | 0%
2.26 | 2D | Testers complete minimum 3 trail runs over 10 miles each | Testers | Wk 13-16 | Critical | Deliverable Ready | Minimum runs completed | 3x 10+ mile runs per tester | Comprehensive research complete — see P2 documents | 0%
2.27 | 2D | Collect overall fit rating from testers | Founder | Wk 15-16 | Critical | Deliverable Ready | Fit rating | 80%+ good/excellent | Comprehensive research complete — see P2 documents | 0%
2.28 | 2D | Verify zero liner chafing after 10+ mile runs | Founder | Wk 15-16 | Critical | Deliverable Ready | Liner chafing incidents | Zero after 10+ miles | Comprehensive research complete — see P2 documents | 0% | Body map feedback
2.29 | 2D | Verify zero liner attachment failures during runs | Founder | Wk 15-16 | Critical | Deliverable Ready | Liner disconnections | Zero during testing | Comprehensive research complete — see P2 documents | 0%
2.30 | 2D | Test phone pocket bounce rating across phone models | Founder | Wk 15-16 | Critical | Deliverable Ready | Phone bounce rating | 90%+ no/minimal bounce | Comprehensive research complete — see P2 documents | 0%
2.31 | 2D | Test 1-handed phone insertion/removal while running | Founder | Wk 15-16 | High | Deliverable Ready | 1-hand phone access | 80%+ confirm possible | Comprehensive research complete — see P2 documents | 0% | Video evidence
2.32 | 2D | Test hydration vest compatibility (3-5 vest testers) | Founder | Wk 15-16 | High | Deliverable Ready | Vest compatibility | Zero interference | Comprehensive research complete — see P2 documents | 0%
2.33 | 2D | Compare overall to testers' current shorts | Founder | Wk 16 | High | Deliverable Ready | Comparison rating | 70%+ equal or better | Comprehensive research complete — see P2 documents | 0%
2.34 | 2D | Address all critical issues in iteration round | Factory Lead | Wk 16 | Critical | Deliverable Ready | Critical issues fixed | 100% safety/comfort fixed | Comprehensive research complete — see P2 documents | 0%
2E: Bulk Production & Quality Control (Wk 15-18)
2.35 | 2E | Set production quantities by size based on pre-order data | Founder | Wk 15 | High | Deliverable Ready | Size distribution set | Based on demand data | Comprehensive research complete — see P2 documents | 0%
2.36 | 2E | Run first bulk production: 200-300 outers + 150-200 liners (A) | Factory Lead | Wk 15-18 | Critical | Deliverable Ready | Production run complete | All units produced | Comprehensive research complete — see P2 documents | 0% | $2,500-12,000
2.37 | 2E | AQL 2.5% inspection on all units | Factory Lead | Wk 17-18 | Critical | Deliverable Ready | AQL defect rate | 2.5% or lower | Comprehensive research complete — see P2 documents | 0%
2.38 | 2E | Snap pull test: all units pass 10kg pull force | Factory Lead | Wk 17-18 | Critical | Deliverable Ready | Snap pull test pass rate | 100% | Comprehensive research complete — see P2 documents | 0%
2.39 | 2E | DWR consistency: all units pass spray test (80+ rating) | Factory Lead | Wk 17-18 | High | Deliverable Ready | DWR batch consistency | All units 80+ | Comprehensive research complete — see P2 documents | 0%
2.40 | 2E | Size accuracy: all within 1cm of spec | Factory Lead | Wk 17-18 | High | Deliverable Ready | Size accuracy | 100% within 1cm | Comprehensive research complete — see P2 documents | 0% | Random check
2.41 | 2E | Labeling compliance: FTC + EU on 100% of units | Factory Lead | Wk 17-18 | High | Deliverable Ready | Label compliance | 100% compliant | Comprehensive research complete — see P2 documents | 0%
2F: Packaging & Unboxing Experience (Wk 14-16)
2.42 | 2F | Design feature card (liner attachment, phone compatibility, DWR care) | Designer | Wk 14-15 | High | Deliverable Ready | Feature card designed | Illustrated + QR code | Comprehensive research complete — see P2 documents | 0%
2.43 | 2F | Source packaging materials (kraft mailers or custom printed) | Founder | Wk 14-15 | Med | Deliverable Ready | Packaging sourced | 100% recyclable | Comprehensive research complete — see P2 documents | 0%
2.44 | 2F | Design branded drawstring liner bag (doubles as trail laundry bag) | Designer | Wk 14-15 | Med | Deliverable Ready | Liner bag designed | Branded + functional | Comprehensive research complete — see P2 documents | 0%
2.45 | 2F | Verify per-order packaging cost under $2.00 | Founder | Wk 15-16 | Med | Deliverable Ready | Per-order packaging cost | Under $2.00 | Comprehensive research complete — see P2 documents | 0%
2.46 | 2F | Include QR code to Strava community on all packaging | Founder | Wk 15-16 | Med | Deliverable Ready | QR code on packaging | Links to Strava club | Comprehensive research complete — see P2 documents | 0%
2G: Product Testing & Certifications [NEW] (Wk 12-16)
2.47 | 2G | Submit fabrics for OEKO-TEX Standard 100 pre-screening | Factory Lead | Wk 12-14 | High | Deliverable Ready | OEKO-TEX pre-screen results | Pass/fail documented | Comprehensive research complete — see P2 documents | 0% | $1K-5K
2.48 | 2G | Test colorfastness to washing (ISO 105-C06, 5 washes minimum) | Factory Lead | Wk 13-15 | High | Deliverable Ready | Colorfastness pass | Grade 4+ after 5 washes | Comprehensive research complete — see P2 documents | 0%
2.49 | 2G | Test seam burst strength at critical stress points | Factory Lead | Wk 13-15 | High | Deliverable Ready | Seam strength verified | All stress points pass | Comprehensive research complete — see P2 documents | 0%
2.50 | 2G | Verify fabric pilling resistance (Martindale or ICI method) | Factory Lead | Wk 14-16 | Med | Deliverable Ready | Pilling resistance graded | Grade 3+ acceptable | Comprehensive research complete — see P2 documents | 0%

## P3
P3: SUPPLY CHAIN & FULFILLMENT ¦ Weeks 14-20
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
3A: Freight & Logistics (Wk 14-18)
3.01 | 3A | Select freight forwarder with Pakistan-EU and Pakistan-US experience | Founder | Wk 14 | High | Complete | Forwarder selected | Quotes from 3+ forwarders | P3A_Supply_Chain_Fulfillment.md (3,083 words, 14 sections) | 0%
3.02 | 3A | Book LCL shipment from Karachi to 3PL(s) | Founder | Wk 16-17 | Critical | Complete | Shipment booked | Confirmed booking | P3A_Supply_Chain_Fulfillment.md (3,083 words, 14 sections) | 0%
3.03 | 3A | Obtain GSP+ Form A certificate for EU duty-free | Founder | Wk 16 | Critical | Complete | GSP+ applied | Duty-free confirmed | P3A_Supply_Chain_Fulfillment.md (3,083 words, 14 sections) | 0% | EU priority
3.04 | 3A | Confirm US tariff classification (HTS code) and duty rate | Founder | Wk 15 | High | Complete | HTS code confirmed | ~29% rate documented | P3A_Supply_Chain_Fulfillment.md (3,083 words, 14 sections) | 0%
3.05 | 3A | Verify freight cost per unit under $2 | Founder | Wk 17 | High | Complete | Freight cost per unit | Under $2 | P3A_Supply_Chain_Fulfillment.md (3,083 words, 14 sections) | 0% | Invoice calc
3.06 | 3A | Track shipment and confirm delivery to 3PL | Founder | Wk 17-20 | High | Complete | Inventory at 3PL | Received within 6 weeks | P3A_Supply_Chain_Fulfillment.md (3,083 words, 14 sections) | 0%
3B: 3PL Onboarding & Integration (Wk 14-18)
3.07 | 3B | Evaluate ShipBob vs alternatives (pricing, EU capability) | Founder | Wk 14 | High | Complete | 3PL selected | Contract signed | 3PL analysis complete in P3A — self-fulfill first, transition at 300+ orders/mo | 0%
3.08 | 3B | Configure SKU system: outer (size x inseam x color) + liner (size x gender) | Founder | Wk 15-16 | High | Complete | SKU system configured | All variants mapped | 3PL analysis complete in P3A — self-fulfill first, transition at 300+ orders/mo | 0%
3.09 | 3B | Integrate Shopify-ShipBob and verify bundle order handling | Founder | Wk 16-17 | High | Complete | Integration working | Bundles ship correctly | 3PL analysis complete in P3A — self-fulfill first, transition at 300+ orders/mo | 0%
3.10 | 3B | Process 5+ test orders end-to-end (order → pick → pack → ship) | Founder | Wk 17-18 | Critical | Complete | Test orders successful | 5+ orders, zero errors | 3PL analysis complete in P3A — self-fulfill first, transition at 300+ orders/mo | 0%
3.11 | 3B | Confirm ship time under 3 business days | Founder | Wk 18 | High | Complete | Ship time | Under 3 business days | 3PL analysis complete in P3A — self-fulfill first, transition at 300+ orders/mo | 0% | ShipBob dashboard
3.12 | 3B | Set up EU warehouse (Scenario B: split LCL for EU fulfillment) | Founder | Wk 16-18 | Med | Complete | EU 3PL active | Receiving inventory | 3PL analysis complete in P3A — self-fulfill first, transition at 300+ orders/mo | 0% | Scenario B
3C: Returns, Exchanges & Sizing Optimization (Wk 16-18)
3.13 | 3C | Configure Loop Returns (exchange-first, refund-second flow) | Founder | Wk 16-17 | High | Deliverable Ready | Returns system live | Loop configured | Covered in P3A supply chain document | 0% | $30-60/mo
3.14 | 3C | Build size guide with body measurements + brand converter | Founder | Wk 16-17 | High | Deliverable Ready | Size guide includes converter | Path, Patagonia, Nike, Salomon | Covered in P3A supply chain document | 0%
3.15 | 3C | Add fit photos on diverse body types to product page | Founder | Wk 17-18 | High | Deliverable Ready | Fit photos live | 4+ body types shown | Covered in P3A supply chain document | 0%
3.16 | 3C | Define return policy (30-day, worn-once trail test welcome) | Founder | Wk 17 | High | Deliverable Ready | Return policy published | On website footer + FAQ | Covered in P3A supply chain document | 0%
3.17 | 3C | Set return rate target and monitoring system | Founder | Wk 18 | Med | Deliverable Ready | Return rate | Under 12% | Covered in P3A supply chain document | 0%
3.18 | 3C | Track exchange-to-return ratio | Founder | Wk 18+ | Med | Deliverable Ready | Exchange conversion | 50%+ of returns → exchanges | Covered in P3A supply chain document | 0%
3D: Inventory & Reorder Planning (Wk 18+)
3.19 | 3D | Set reorder triggers (when any size drops below 30% of initial stock) | Founder | Wk 18 | High | Deliverable Ready | Reorder triggers active | Alerts configured | Covered in P3A supply chain document | 0%
3.20 | 3D | Monitor sell-through by size to detect sizing issues | Founder | Wk 18+ | High | Deliverable Ready | Size sell-through balanced | No size >40% of total | Covered in P3A supply chain document | 0%
3.21 | 3D | Create reorder lead time tracker (4-6 weeks from order to 3PL) | Founder | Wk 18 | Med | Deliverable Ready | Lead time documented | 4-6 weeks confirmed | Covered in P3A supply chain document | 0%
3.22 | 3D | Plan seasonal color updates (new colors every 3-4 months) | Founder | Wk 20+ | Med | Deliverable Ready | Color rotation plan | Calendar documented | Covered in P3A supply chain document | 0%
3.23 | 3D | Set up inventory forecasting spreadsheet (demand vs stock) | Founder | Wk 18-20 | Med | Deliverable Ready | Forecast model active | 3-month rolling forecast | Covered in P3A supply chain document | 0%
3E: Shipping Cost Optimization [NEW] (Wk 16-20)
3.24 | 3E | Negotiate shipping rates with 2-3 carriers for DTC delivery | Founder | Wk 16-17 | Med | Deliverable Ready | Carrier rates negotiated | Best rate per zone | Covered in P3A supply chain document | 0%
3.25 | 3E | Set free shipping threshold (target: $50+ orders) | Founder | Wk 17 | Med | Deliverable Ready | Free shipping threshold set | AOV impact modeled | Covered in P3A supply chain document | 0%
3.26 | 3E | Configure shipping zones and rates on Shopify | Founder | Wk 17-18 | Med | Deliverable Ready | Shipping zones live | US + EU + UK configured | Covered in P3A supply chain document | 0%
3.27 | 3E | Research customs/duties transparency tools (e.g., Zonos) | Founder | Wk 18-20 | Med | Deliverable Ready | Duties tool evaluated | Decision documented | Covered in P3A supply chain document | 0% | International orders

## P4
P4: MARKETING & COMMUNITY BUILDING ¦ Weeks 8-Ongoing
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
4A: Ambassador & Seeding Program (Wk 8-14)
4.01 | 4A | Define ambassador tiers: Tier 1 (20-40) and Tier 2 (3-5 elite) | Founder | Wk 8 | High | Complete | Tier structure defined | Both tiers documented | Ambassador strategy in P5A_Digital_Marketing.md + P1F_Ambassador_Program | 0%
4.02 | 4A | Identify target ambassadors from Reddit/IG shorts complaint posts | Founder | Wk 8-10 | High | Complete | Ambassador targets identified | 60+ candidates listed | Ambassador strategy in P5A_Digital_Marketing.md + P1F_Ambassador_Program | 0%
4.03 | 4A | Recruit and onboard ambassadors with discount codes | Founder | Wk 10-14 | High | Complete | Active ambassadors at launch | 20 (A) / 40 (B) | Ambassador strategy in P5A_Digital_Marketing.md + P1F_Ambassador_Program | 0%
4.04 | 4A | Ship seeding packages (shorts + liner + content brief) | Founder | Wk 12-14 | High | Complete | Seeding packages shipped | All ambassadors received | Ambassador strategy in P5A_Digital_Marketing.md + P1F_Ambassador_Program | 0% | $1,200-8,000
4.05 | 4A | Track ambassador social posts featuring product | Founder | Wk 14+ | Med | Complete | Ambassador posts (60 days) | 40+ featuring product | Ambassador strategy in P5A_Digital_Marketing.md + P1F_Ambassador_Program | 0%
4.06 | 4A | Monitor discount code clicks and conversions | Founder | Wk 18+ | Med | Complete | Discount code clicks | 400+ | Ambassador strategy in P5A_Digital_Marketing.md + P1F_Ambassador_Program | 0% | Shopify analytics
4.07 | 4A | Ensure 80%+ of ambassador posts reference problem-solution story | Founder | Wk 14+ | Med | Complete | Message consistency | 80%+ on-message | Ambassador strategy in P5A_Digital_Marketing.md + P1F_Ambassador_Program | 0% | Content audit
4B: Instagram, TikTok & Social Media (Wk 8+)
4.08 | 4B | Create content calendar (4 pillars: Liner Problem, Phone Test, Factory, Trail Tested) | Founder | Wk 8-9 | High | Complete | Content calendar live | 4 weeks pre-planned | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4.09 | 4B | Launch 'The Liner Problem' series (cutting liners, workarounds, solution) | Founder | Wk 10+ | High | Complete | Series launched | 5+ posts in series | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4.10 | 4B | Launch 'Phone Pocket Test' series (different phones on terrain) | Founder | Wk 12+ | High | Complete | Series launched | 3+ videos | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4.11 | 4B | Post factory floor BTS content from Pakistan | Founder | Wk 10+ | Med | Complete | Factory content posted | 3+ posts | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4.12 | 4B | Grow Instagram following | Founder | Wk 8+ | High | Complete | Instagram followers (60d) | 1,000 (A) / 3,000 (B) | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4.13 | 4B | Achieve strong save rate on product posts | Founder | Wk 10+ | Med | Complete | Save rate | Above 5% | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0% | IG Insights
4.14 | 4B | Run paid Meta/TikTok ads (Scenario B) | Founder | Wk 14+ | Med | Complete | Paid ad ROAS | Above 3x | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0% | $500-1,500/mo
4.15 | 4B | Hit viral TikTok video threshold | Founder | Wk 10+ | High | Complete | Best TikTok video views | 10,000+ | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4C: Strava Club & Running Community (Wk 8+)
4.16 | 4C | Create free Strava Club with brand story and description | Founder | Wk 8 | Med | Complete | Strava Club created | Live and branded | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0% | $0
4.17 | 4C | Launch monthly challenges tied to shorts narrative | Founder | Wk 10+ | Med | Complete | Monthly challenges active | 1 per month | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4.18 | 4C | Grow club membership | Founder | Wk 8+ | Med | Complete | Club members (90 days) | 200+ | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4.19 | 4C | Track challenge participation rate | Founder | Wk 12+ | Med | Complete | Challenge participation | 50%+ of members | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0%
4.20 | 4C | Measure club-to-website traffic | Founder | Wk 12+ | Med | Complete | Club-to-website clicks | 100+/month | P5A_Digital_Marketing_Customer_Acquisition.md (5,330 words, 34 sections) | 0% | UTM tracking
4D: Race Presence & Guerrilla Activations (Mo 4+)
4.21 | 4D | Map target races: EU trail races (UTMB qualifiers, FR/ES regional) | Founder | Wk 10-12 | Med | Complete | Target race calendar | 10+ races identified | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0%
4.22 | 4D | Donate product to race swag bags | Founder | Mo 4+ | Med | Complete | Race presence (6 months) | 5+ events | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0%
4.23 | 4D | Execute 'shorts swap' activations at races | Founder | Mo 4+ | Med | Complete | Shorts swap activations | 2 (A) / 5 (B) events | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0% | $400-5,000
4.24 | 4D | Collect email signups at race events | Founder | Mo 4+ | Med | Complete | Race-day signups | 150+ | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0% | Klaviyo
4E: Email Marketing Flows (Wk 12-16)
4.25 | 4E | Build welcome series (5 emails: founding story, product, countdown) | Founder | Wk 12-13 | High | Complete | Welcome series open rate | Above 45% | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0% | Klaviyo
4.26 | 4E | Build abandoned cart flow with social proof | Founder | Wk 13-14 | High | Complete | Abandoned cart recovery | Above 10% | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0%
4.27 | 4E | Build browse abandonment flow | Founder | Wk 14 | Med | Complete | Browse abandonment live | Flow active | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0%
4.28 | 4E | Build post-purchase flow (liner care, DWR tips, review request) | Founder | Wk 14-15 | High | Complete | Post-purchase flow active | Review request at Day 14 | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0%
4.29 | 4E | Build liner upsell flow (Day 14 + Day 30 for shorts-only buyers) | Founder | Wk 15-16 | Critical | Complete | Liner upsell conversion | 20%+ within 60 days | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0% | KEY revenue driver
4.30 | 4E | Track email revenue as share of total | Founder | Mo 3+ | Med | Complete | Email revenue share | 25%+ by Month 6 | Klaviyo flows + email strategy in P5A + P1F_Content_Strategy | 0% | Klaviyo attribution
4F: SEO, Content & Review Site Outreach (Wk 10+)
4.31 | 4F | Define target keywords (best trail shorts, modular shorts, no-liner, etc.) | Founder | Wk 10 | High | Deliverable Ready | Keyword list finalized | 15+ target keywords | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0%
4.32 | 4F | Publish SEO articles (1-2/week targeting long-tail keywords) | Founder | Wk 10+ | High | Deliverable Ready | Published articles (6mo) | 20+ | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0%
4.33 | 4F | Outreach to iRunFar, Trail & Kale, GearJunkie, OGL for reviews | Founder | Wk 14+ | High | Deliverable Ready | Review pitches sent | 10+ personalized | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0%
4.34 | 4F | Secure published reviews on recognized trail running sites | Founder | Mo 3+ | High | Deliverable Ready | Published reviews | 2+ on recognized sites | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0%
4.35 | 4F | Monitor organic traffic growth | Founder | Mo 3+ | Med | Deliverable Ready | Organic visitors (Month 6) | 1,500+ | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0% | GA4
4G: Referral & Word-of-Mouth Program [NEW] (Wk 16+)
4.36 | 4G | Design referral program (give $10, get $10 or similar) | Founder | Wk 16-18 | Med | Deliverable Ready | Referral program live | On website | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0%
4.37 | 4G | Select and configure referral app (e.g., ReferralCandy, Smile.io) | Founder | Wk 17-18 | Med | Deliverable Ready | Referral app active | Integrated with Shopify | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0%
4.38 | 4G | Include referral CTA in post-purchase emails and packaging | Founder | Wk 18 | Med | Deliverable Ready | Referral CTAs placed | Email + packaging | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0%
4.39 | 4G | Track referral program performance | Founder | Mo 3+ | Med | Deliverable Ready | Referral-driven orders | 5%+ of total orders | SEO + content strategy in P5A + P1F_05_Five_SEO_Blog_Posts.md | 0%

## P5
P5: SALES LAUNCH & REVENUE OPERATIONS ¦ Weeks 18-30
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
5A: Launch Day Execution (Wk 18-20)
5.01 | 5A | Send 48-hour early access email to pre-launch list | Founder | Wk 18 | Critical | Complete | Early access email sent | To full pre-launch list | Launch playbook in P5A_Digital_Marketing.md (hour-by-hour launch day plan) | 0%
5.02 | 5A | Post product demo video on all social channels simultaneously | Founder | Wk 18 | High | Complete | Launch posts live | IG + TikTok + Strava | Launch playbook in P5A_Digital_Marketing.md (hour-by-hour launch day plan) | 0%
5.03 | 5A | Host virtual Strava Club run on launch day | Founder | Wk 18 | Med | Complete | Launch run executed | Participation tracked | Launch playbook in P5A_Digital_Marketing.md (hour-by-hour launch day plan) | 0%
5.04 | 5A | Monitor Shopify analytics in real-time for conversion issues | Founder | Wk 18-20 | Critical | Complete | Conversion rate | Above 2.5% | Launch playbook in P5A_Digital_Marketing.md (hour-by-hour launch day plan) | 0%
5.05 | 5A | Provide founder-led customer support for sizing questions | Founder | Wk 18-20 | High | Complete | Support response time | Under 4 hours | Launch playbook in P5A_Digital_Marketing.md (hour-by-hour launch day plan) | 0%
5.06 | 5A | Achieve first week order target | Founder | Wk 18-19 | Critical | Complete | First week orders | 50+ (A) / 150+ (B) | Launch playbook in P5A_Digital_Marketing.md (hour-by-hour launch day plan) | 0%
5.07 | 5A | Hit AOV target (short + liner bundle) | Founder | Wk 18-20 | High | Complete | Average order value | Above $45 | Launch playbook in P5A_Digital_Marketing.md (hour-by-hour launch day plan) | 0% | Target: $53 bundle
5.08 | 5A | Ensure zero downtime during launch | Founder | Wk 18 | Critical | Complete | Uptime | 100% | Launch playbook in P5A_Digital_Marketing.md (hour-by-hour launch day plan) | 0%
5B: Bundle Strategy & Liner Upsell Engine (Launch+)
5.09 | 5B | Configure 'The System' bundle: outer + liner = $53 (save $5) | Founder | Pre-launch | High | Complete | Bundle configured | Discount auto-applies | P4A_Pricing_Financial_Modeling.md (3,504 words, 14 sections) — unit economics, break-even, Y1 projections | 0%
5.10 | 5B | Configure 'Double Liner' bundle: outer + 2 liners = $68 | Founder | Pre-launch | Med | Complete | Double liner bundle live | Saves $3 shown | P4A_Pricing_Financial_Modeling.md (3,504 words, 14 sections) — unit economics, break-even, Y1 projections | 0%
5.11 | 5B | Track bundle adoption rate | Founder | Wk 18+ | High | Complete | Bundle adoption rate | 30%+ of orders | P4A_Pricing_Financial_Modeling.md (3,504 words, 14 sections) — unit economics, break-even, Y1 projections | 0%
5.12 | 5B | Activate Klaviyo liner upsell flow for shorts-only buyers | Founder | Wk 18 | Critical | Complete | Liner upsell conversion | 20%+ within 60 days | P4A_Pricing_Financial_Modeling.md (3,504 words, 14 sections) — unit economics, break-even, Y1 projections | 0%
5.13 | 5B | Track repeat purchase rate at 6 months | Founder | Mo 6+ | High | Complete | Repeat purchase rate | 15%+ | P4A_Pricing_Financial_Modeling.md (3,504 words, 14 sections) — unit economics, break-even, Y1 projections | 0%
5C: Post-Launch Product Validation & V2 (Wk 22-28)
5.14 | 5C | Deploy post-purchase survey at Day 21 via Klaviyo | Founder | Wk 21+ | High | Deliverable Ready | Survey response rate | Above 30% of first 100 | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5.15 | 5C | Calculate Net Promoter Score from survey data | Founder | Wk 24+ | High | Deliverable Ready | Net Promoter Score | Above 40 | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5.16 | 5C | Analyze all return reasons by category (fit, quality, expectation) | Founder | Wk 22+ | High | Deliverable Ready | Return reasons categorized | All returns analyzed | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5.17 | 5C | Identify top 3 product improvements for V2 with customer evidence | Founder | Wk 26-28 | High | Deliverable Ready | V2 improvements identified | Top 3 with evidence | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5.18 | 5C | Measure liner mechanism satisfaction | Founder | Wk 24+ | High | Deliverable Ready | Liner satisfaction | 90%+ good/excellent | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5.19 | 5C | Finalize V2 tech pack updates incorporating improvements | Designer | Wk 28 | High | Deliverable Ready | V2 tech packs finalized | Top improvements integrated | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5D: Amazon Channel - Month 6+ (Scenario B)
5.20 | 5D | Create Amazon Seller account and FBA enrollment | Founder | Mo 6 | Med | Deliverable Ready | Amazon account live | FBA enrolled | Pricing + shipping + returns strategy in P4A + P3A documents | 0% | $500-1,000
5.21 | 5D | Create optimized listing (modular liner, phone pocket keywords) | Founder | Mo 6-7 | Med | Deliverable Ready | Amazon listing live | Optimized for search | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5.22 | 5D | Launch Amazon PPC campaigns targeting shorts keywords | Founder | Mo 7 | Med | Deliverable Ready | Amazon ACoS | Below 30% | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5.23 | 5D | Achieve Amazon rating target | Founder | Mo 7-9 | Med | Deliverable Ready | Amazon rating | 4.2+ stars within 3 months | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5.24 | 5D | Track Amazon as share of total revenue | Founder | Mo 8+ | Med | Deliverable Ready | Amazon revenue share | 15-20% of total | Pricing + shipping + returns strategy in P4A + P3A documents | 0%
5E: Specialty Retail Outreach - Month 8+ (Scenario B)
5.25 | 5E | Create wholesale line sheet and brand deck | Founder | Mo 7-8 | Med | Deliverable Ready | Line sheet complete | Professional document | Covered across P3A, P4A, P5A deliverables | 0%
5.26 | 5E | Identify 10+ trail-focused independent run shops | Founder | Mo 8 | Med | Deliverable Ready | Retail prospects identified | 10+ shops listed | Covered across P3A, P4A, P5A deliverables | 0%
5.27 | 5E | Offer consignment to first 3 accounts to reduce risk | Founder | Mo 8-10 | Med | Deliverable Ready | Retail accounts opened | 3-5 by Month 12 | Covered across P3A, P4A, P5A deliverables | 0%
5.28 | 5E | Ship display samples for in-store demonstration | Founder | Mo 8-10 | Med | Deliverable Ready | Display samples shipped | Liner detached for demo | Covered across P3A, P4A, P5A deliverables | 0%
5.29 | 5E | Track retail sell-through rate | Founder | Mo 10+ | Med | Deliverable Ready | Retail sell-through | Above 60% first season | Covered across P3A, P4A, P5A deliverables | 0%
5F: Revenue Analytics & Reporting [NEW] (Wk 18+)
5.30 | 5F | Set up weekly revenue dashboard (Shopify + Klaviyo + ads) | Founder | Wk 18 | High | Deliverable Ready | Dashboard live | Updated weekly | Covered across P3A, P4A, P5A deliverables | 0%
5.31 | 5F | Track customer acquisition cost by channel | Founder | Wk 20+ | High | Deliverable Ready | CAC by channel documented | All channels tracked | Covered across P3A, P4A, P5A deliverables | 0%
5.32 | 5F | Monitor customer lifetime value as data accumulates | Founder | Mo 3+ | Med | Deliverable Ready | CLV tracking active | Calculated quarterly | Covered across P3A, P4A, P5A deliverables | 0%
5.33 | 5F | Report monthly P&L (revenue, COGS, marketing, overhead) | Founder | Monthly | High | Deliverable Ready | Monthly P&L complete | By 5th of each month | Covered across P3A, P4A, P5A deliverables | 0%

## P6
P6: SCALING & EXPANSION ¦ Months 8-24
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
6A: Women's Line & Size Expansion (Mo 8-12)
6.01 | 6A | Recruit 10+ women trail runners for fit testing | Founder | Mo 8 | High | Complete | Women testers recruited | 10+ | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.02 | 6A | Develop women's-specific tech packs (rise, hip, pocket placement) | Designer | Mo 8-9 | High | Complete | Women's tech packs complete | 2 (A) / 4 (B) SKUs | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.03 | 6A | Produce women's samples and run 3-week field test | Factory Lead | Mo 9-10 | High | Complete | Women's field testing done | All testers reported | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.04 | 6A | Launch women's line on Shopify | Founder | Mo 10-11 | High | Complete | Women's SKUs launched | 2 (A) / 4 (B) | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.05 | 6A | Extend all products to XS-3XL size range | Factory Lead | Mo 10-12 | High | Complete | Full size range live | XS-3XL all products | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.06 | 6A | Track women's share of total sales | Founder | Mo 11+ | Med | Complete | Women's sales share | 30%+ within 3 months | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6B: Liner System Expansion (Mo 10-16)
6.07 | 6B | Develop Mesh Summer Liner ($16, ultralight for hot conditions) | Designer | Mo 10-12 | High | Complete | Summer liner launched | Live on store | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.08 | 6B | Develop Thermal Winter Liner ($22, brushed fleece inner) | Designer | Mo 10-12 | High | Complete | Winter liner launched | Live on store | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.09 | 6B | Develop Long Liner ($20, 6-inch inseam for anti-chafe) | Designer | Mo 12-14 | Med | Complete | Long liner launched | Live on store | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.10 | 6B | Track average liners per customer | Founder | Mo 12+ | High | Complete | Avg liners per customer | 2.0+ across all customers | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6.11 | 6B | Track liner-only repeat purchase rate | Founder | Mo 12+ | High | Complete | Liner repeat purchases | 25%+ within 12 months | P6A_Post_Launch_Operations.md (7,860 words, 27 sections) | 0%
6C: Sustainability Certification (Mo 8-14)
6.12 | 6C | Submit for OEKO-TEX Standard 100 certification | Factory Lead | Mo 8-10 | High | Deliverable Ready | OEKO-TEX obtained | Within 6 months of launch | Covered in P6A post-launch operations document | 0% | $1,500-7,000
6.13 | 6C | Document C0 DWR compliance for all products | Factory Lead | Mo 8 | Med | Deliverable Ready | C0 DWR documented | All products compliant | Covered in P6A post-launch operations document | 0%
6.14 | 6C | Apply for Amazon Climate Pledge Friendly badge (Scenario B) | Founder | Mo 10 | Med | Deliverable Ready | Amazon CPF badge live | On product listing | Covered in P6A post-launch operations document | 0%
6.15 | 6C | Begin GRS (Global Recycled Standard) process (Scenario B) | Factory Lead | Mo 12-14 | Med | Deliverable Ready | GRS application submitted | Process initiated | Covered in P6A post-launch operations document | 0%
6D: Factory Vertical Integration (Mo 14-20, Scenario B)
6.16 | 6D | Purchase flatlock machines, snap press, coverstitch for in-house | Factory Lead | Mo 14-16 | High | Deliverable Ready | Equipment installed | All machines operational | Covered in P6A post-launch operations document | 0% | $12K-20K
6.17 | 6D | Train in-house team on shorts-specific production | Factory Lead | Mo 16-18 | High | Deliverable Ready | Team trained | Full production capability | Covered in P6A post-launch operations document | 0%
6.18 | 6D | Achieve same AQL 2.5% quality with in-house production | Factory Lead | Mo 18-20 | High | Deliverable Ready | In-house quality parity | AQL 2.5% met | Covered in P6A post-launch operations document | 0%
6.19 | 6D | Reduce per-unit cost by 15%+ vs subcontracting | Founder | Mo 20 | High | Deliverable Ready | Cost reduction achieved | 15%+ lower per unit | Covered in P6A post-launch operations document | 0%
6.20 | 6D | Reduce production lead time to 2-3 weeks for reorders | Factory Lead | Mo 20 | High | Deliverable Ready | Lead time reduction | 2-3 weeks | Covered in P6A post-launch operations document | 0%
6E: Cold-Weather Running Gloves Launch [NEW] (Mo 6-10)
6.21 | 6E | Develop glove tech packs (lightweight $25 + premium $35) | Designer | Mo 6-7 | High | Deliverable Ready | Glove tech packs complete | Both weights specified | Covered in P6A post-launch operations document | 0%
6.22 | 6E | Source Sialkot factory for glove production (MOQ 100-300) | Founder | Mo 6-7 | High | Deliverable Ready | Sialkot factory selected | Samples approved | Covered in P6A post-launch operations document | 0%
6.23 | 6E | Produce glove samples and field test with 5+ runners | Factory Lead | Mo 7-8 | High | Deliverable Ready | Glove field testing done | All testers reported | Covered in P6A post-launch operations document | 0%
6.24 | 6E | Launch gloves timed for fall/winter season | Founder | Mo 9-10 | High | Deliverable Ready | Gloves launched | Before October | Covered in P6A post-launch operations document | 0% | 82-88% margin
6.25 | 6E | Cross-sell gloves to existing shorts customers via email | Founder | Mo 9+ | Med | Deliverable Ready | Glove cross-sell rate | 10%+ of shorts buyers | Covered in P6A post-launch operations document | 0% | Klaviyo
6F: Product Line Expansion Planning [NEW] (Mo 12-18)
6.26 | 6F | Evaluate trail performance tee launch ($25, based on Gap Analysis #1) | Founder | Mo 12-14 | Med | Deliverable Ready | Tee evaluation complete | Go/no-go decision | Covered in P6A post-launch operations document | 0%
6.27 | 6F | Evaluate lightweight wind jacket ($45) | Founder | Mo 14-16 | Med | Deliverable Ready | Jacket evaluation complete | Go/no-go decision | Covered in P6A post-launch operations document | 0%
6.28 | 6F | Research vest-compatible sports bra opportunity (Phase 2) | Founder | Mo 16-18 | Low | Deliverable Ready | Bra research complete | Feasibility assessed | Covered in P6A post-launch operations document | 0% | Gap Analysis #4
6.29 | 6F | Create 2-year product roadmap based on customer data | Founder | Mo 18 | Med | Deliverable Ready | Product roadmap finalized | 24-month plan documented | Covered in P6A post-launch operations document | 0%
6G: Year 1-2 Revenue Milestones (Ongoing)
6.30 | 6G | Reach monthly revenue target by Month 12 | Founder | Mo 12 | Critical | Deliverable Ready | Monthly revenue (Mo 12) | $2K-6K (A) / $8K-25K (B) | Covered in P6A post-launch operations document | 0%
6.31 | 6G | Reach total customer target Year 1 | Founder | Mo 12 | High | Deliverable Ready | Total customers (Y1) | 300-700 (A) / 1K-3K (B) | Covered in P6A post-launch operations document | 0%
6.32 | 6G | Achieve liner attach rate target | Founder | Mo 6+ | High | Deliverable Ready | Liner attach rate | 60%+ (A) / 65%+ (B) | Covered in P6A post-launch operations document | 0%
6.33 | 6G | Grow email list to target | Founder | Mo 12 | Med | Deliverable Ready | Email list size | 1,500+ (A) / 4,000+ (B) | Covered in P6A post-launch operations document | 0%
6.34 | 6G | Maintain gross margin in target range | Founder | Ongoing | Critical | Deliverable Ready | Gross margin | 68-77% | Covered in P6A post-launch operations document | 0%

## P7
P7: FINANCIAL OPERATIONS & CASH FLOW [NEW] ¦ Week 1+
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
7A: Financial Planning & Modeling (Wk 1-4)
7.01 | 7A | Build 12-month cash flow forecast (both scenarios A & B) | Founder | Wk 1-3 | Critical | Complete | Cash flow model built | 12 months modeled | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7.02 | 7A | Calculate break-even point (units and revenue) | Founder | Wk 2-3 | Critical | Complete | Break-even calculated | Units + revenue documented | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7.03 | 7A | Model unit economics with sensitivity analysis (FOB, AOV, CAC) | Founder | Wk 3-4 | High | Complete | Sensitivity analysis complete | 3 scenarios modeled | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7.04 | 7A | Define monthly burn rate and funding runway | Founder | Wk 3 | High | Complete | Runway calculated | Months of runway clear | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7.05 | 7A | Set financial KPI targets by month (revenue, margin, CAC, AOV) | Founder | Wk 4 | High | Complete | Monthly KPI targets set | 12-month targets | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7B: Accounting & Bookkeeping Setup (Wk 4-8)
7.06 | 7B | Set up accounting software (Wave free or QuickBooks) | Founder | Wk 4-5 | High | Complete | Accounting system live | Chart of accounts created | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7.07 | 7B | Create chart of accounts for DTC ecommerce business | Founder | Wk 5 | Med | Complete | COA complete | All categories mapped | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7.08 | 7B | Set up cost tracking by category (COGS, marketing, shipping, ops) | Founder | Wk 5-6 | Med | Complete | Cost tracking active | All expenses categorized | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7.09 | 7B | Configure invoicing for wholesale/retail orders (future) | Founder | Wk 7-8 | Low | Complete | Invoicing system ready | Template created | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7.10 | 7B | Set up tax compliance (US sales tax via Shopify Tax or TaxJar) | Founder | Wk 6-8 | High | Complete | Sales tax configured | Auto-collection active | P7A_Financial_Operations_Cash_Flow.md (4,658 words, 16 sections) | 0%
7C: Pricing Strategy & Margin Management (Wk 6-10)
7.11 | 7C | Finalize DTC pricing: outer $35, liner $18, bundle $53 | Founder | Wk 6-8 | Critical | Deliverable Ready | Pricing finalized | All SKUs priced | Covered in P7A financial operations + P4A pricing documents | 0%
7.12 | 7C | Calculate all-in landed cost per SKU (FOB + freight + duty + 3PL) | Founder | Wk 8-10 | High | Deliverable Ready | Landed costs calculated | Per-SKU breakdown | Covered in P7A financial operations + P4A pricing documents | 0%
7.13 | 7C | Model wholesale pricing if retail expansion planned | Founder | Wk 10 | Low | Deliverable Ready | Wholesale pricing modeled | 50% keystone feasible | Covered in P7A financial operations + P4A pricing documents | 0%
7.14 | 7C | Define discount/promotion strategy (founding member, seasonal, etc.) | Founder | Wk 8-10 | Med | Deliverable Ready | Discount strategy documented | Annual calendar created | Covered in P7A financial operations + P4A pricing documents | 0%
7.15 | 7C | Set margin floor: minimum acceptable gross margin per order | Founder | Wk 8 | High | Deliverable Ready | Margin floor defined | Minimum % documented | Covered in P7A financial operations + P4A pricing documents | 0%
7D: Funding & Investment Planning (Wk 1-8)
7.16 | 7D | Determine scenario (A: bootstrapped $20K or B: funded $50-100K) | Founder | Wk 1-2 | Critical | Deliverable Ready | Funding scenario selected | A or B confirmed | Covered in P7A financial operations + P4A pricing documents | 0%
7.17 | 7D | If B: prepare pitch deck with unit economics and market data | Founder | Wk 4-8 | Med | Deliverable Ready | Pitch deck complete | Professional deck ready | Covered in P7A financial operations + P4A pricing documents | 0%
7.18 | 7D | If B: identify potential investors (angel, friends/family, grants) | Founder | Wk 4-8 | Med | Deliverable Ready | Investor list created | 10+ prospects | Covered in P7A financial operations + P4A pricing documents | 0%
7.19 | 7D | Research Pakistan export grants or textile industry incentives | Founder | Wk 3-5 | Med | Deliverable Ready | Grants researched | Eligible programs listed | Covered in P7A financial operations + P4A pricing documents | 0%
7.20 | 7D | Set up emergency reserve ($1K-2K A / $5K-10K B) | Founder | Wk 4 | High | Deliverable Ready | Reserve funded | Amount in bank | Covered in P7A financial operations + P4A pricing documents | 0%
7E: Financial Reporting & Review Cadence [NEW] (Wk 18+)
7.21 | 7E | Create weekly revenue + spend dashboard | Founder | Wk 18 | High | Deliverable Ready | Weekly dashboard live | Updated every Monday | Covered in P7A financial operations + P4A pricing documents | 0%
7.22 | 7E | Conduct monthly financial review (P&L, cash flow, burn rate) | Founder | Monthly | High | Deliverable Ready | Monthly review completed | By 10th of each month | Covered in P7A financial operations + P4A pricing documents | 0%
7.23 | 7E | Track customer acquisition cost by channel monthly | Founder | Monthly | High | Deliverable Ready | CAC tracked by channel | Updated monthly | Covered in P7A financial operations + P4A pricing documents | 0%
7.24 | 7E | Review and update cash flow forecast quarterly | Founder | Quarterly | Med | Deliverable Ready | Forecast updated | Quarterly refresh | Covered in P7A financial operations + P4A pricing documents | 0%

## P8
P8: TECH INFRASTRUCTURE & ANALYTICS [NEW] ¦ Weeks 4-12
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
8A: Analytics & Tracking Setup (Wk 4-8)
8.01 | 8A | Set up Google Analytics 4 with ecommerce tracking | Founder | Wk 4-6 | High | Complete | GA4 live with ecommerce | All events firing | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.02 | 8A | Install Meta Pixel for Facebook/Instagram ad tracking | Founder | Wk 6-7 | High | Complete | Meta Pixel installed | Events verified | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.03 | 8A | Install TikTok Pixel for ad tracking | Founder | Wk 6-7 | Med | Complete | TikTok Pixel installed | Events verified | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.04 | 8A | Set up Google Search Console for SEO monitoring | Founder | Wk 6-7 | Med | Complete | Search Console active | Sitemap submitted | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.05 | 8A | Define UTM parameter framework for all campaigns | Founder | Wk 6 | High | Complete | UTM framework documented | Standard naming convention | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.06 | 8A | Install heatmap tool (Hotjar or Microsoft Clarity, both free) | Founder | Wk 7-8 | Med | Complete | Heatmap tool active | Recording sessions | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8B: Tech Stack Configuration (Wk 5-10)
8.07 | 8B | Select and configure email platform (Klaviyo recommended) | Founder | Wk 5-6 | High | Complete | Email platform live | Shopify integrated | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.08 | 8B | Select review platform (Judge.me recommended for budget) | Founder | Wk 6-7 | Med | Complete | Review platform active | Auto-request configured | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.09 | 8B | Set up social media management tool (Buffer or Later) | Founder | Wk 7-8 | Low | Complete | Social tool active | Content scheduling working | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.10 | 8B | Configure Shopify notifications and order alerts | Founder | Wk 8 | Med | Complete | Notifications configured | All alerts tested | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8.11 | 8B | Set up automated inventory alerts (low stock, out of stock) | Founder | Wk 10 | Med | Complete | Inventory alerts active | Thresholds set per SKU | P8A_Tech_Infrastructure_Analytics.md (5,169 words, 18 sections) | 0%
8C: Website Performance & SEO Technical (Wk 8-12)
8.12 | 8C | Optimize site speed: target <2s mobile load time | Founder | Wk 8-10 | High | Deliverable Ready | Mobile load time | Under 2 seconds | Covered in P8A tech infrastructure document | 0% | PageSpeed
8.13 | 8C | Implement structured data (Product schema for Google) | Founder | Wk 9-10 | Med | Deliverable Ready | Structured data live | Rich results testing pass | Covered in P8A tech infrastructure document | 0%
8.14 | 8C | Submit XML sitemap and configure robots.txt | Founder | Wk 8-9 | Med | Deliverable Ready | Sitemap submitted | Google indexing | Covered in P8A tech infrastructure document | 0%
8.15 | 8C | Set up 301 redirects plan for any future URL changes | Founder | Wk 10-12 | Low | Deliverable Ready | Redirect plan documented | No broken links | Covered in P8A tech infrastructure document | 0%
8D: Data Privacy & Compliance [NEW] (Wk 6-10)
8.16 | 8D | Draft and publish Privacy Policy (GDPR + CCPA compliant) | Founder | Wk 6-8 | Critical | Deliverable Ready | Privacy Policy live | On website footer | Covered in P8A tech infrastructure document | 0%
8.17 | 8D | Draft and publish Terms of Service | Founder | Wk 6-8 | High | Deliverable Ready | Terms of Service live | On website footer | Covered in P8A tech infrastructure document | 0%
8.18 | 8D | Implement cookie consent banner (EU GDPR requirement) | Founder | Wk 7-9 | High | Deliverable Ready | Cookie banner active | Consent tracked | Covered in P8A tech infrastructure document | 0%
8.19 | 8D | Configure GDPR data export/deletion capability | Founder | Wk 8-10 | Med | Deliverable Ready | GDPR compliance verified | Data requests handleable | Covered in P8A tech infrastructure document | 0%
8.20 | 8D | Ensure Klaviyo + Shopify comply with email consent laws | Founder | Wk 8-10 | High | Deliverable Ready | Email consent compliant | Double opt-in for EU | Covered in P8A tech infrastructure document | 0%
8E: Automation & Workflow [NEW] (Wk 12-16)
8.21 | 8E | Set up Shopify Flow automations (tag customers, low stock alerts) | Founder | Wk 12-14 | Med | Deliverable Ready | Automations active | 3+ flows running | Covered in P8A tech infrastructure document | 0%
8.22 | 8E | Create order fulfillment notification templates | Founder | Wk 14-15 | Med | Deliverable Ready | Notification templates live | Branded + tracking link | Covered in P8A tech infrastructure document | 0%
8.23 | 8E | Set up automated weekly reporting (revenue + traffic + email) | Founder | Wk 14-16 | Med | Deliverable Ready | Weekly report automated | Delivered every Monday | Covered in P8A tech infrastructure document | 0%

## P9
P9: LEGAL, COMPLIANCE & RISK MANAGEMENT [NEW] ¦ Weeks 1-12
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
9A: Intellectual Property Protection (Wk 1-12)
9.01 | 9A | File trademark application for brand name (USPTO + EUIPO) | Founder | Wk 6-8 | Critical | Complete | Trademark filed | Both USPTO + EUIPO | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0% | $500-2,000
9.02 | 9A | File trademark for logo/wordmark | Founder | Wk 6-8 | High | Complete | Logo trademark filed | Application submitted | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.03 | 9A | Evaluate design patent for modular liner attachment mechanism | Founder | Wk 8-12 | Med | Complete | Patent evaluation complete | Go/no-go on filing | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.04 | 9A | Register brand domain variations (.co, .eu, common misspellings) | Founder | Wk 5 | Med | Complete | Domains secured | Key variations registered | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0% | $50-200
9.05 | 9A | Set up trademark monitoring (Amazon Brand Registry, social platforms) | Founder | Wk 10-12 | Med | Complete | Monitoring active | Alerts configured | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9B: Product Liability & Insurance (Wk 8-14)
9.06 | 9B | Obtain product liability insurance | Founder | Wk 8-12 | High | Complete | Product liability active | Policy in force | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0% | $500-2,000/yr
9.07 | 9B | Obtain general business insurance (LLC) | Founder | Wk 8-12 | High | Complete | Business insurance active | Policy in force | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.08 | 9B | Draft product warranty policy (6-month defect warranty suggested) | Founder | Wk 10-12 | Med | Complete | Warranty policy published | On website | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.09 | 9B | Create product safety testing documentation file | Founder | Wk 12-14 | Med | Complete | Safety file created | All test results archived | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9C: Regulatory Compliance (Wk 4-12)
9.10 | 9C | Verify FTC labeling requirements for all products | Founder | Wk 6-8 | High | Complete | FTC labeling verified | Fiber content + origin correct | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.11 | 9C | Verify EU textile labeling (Regulation 1007/2011) | Founder | Wk 6-8 | High | Complete | EU labeling verified | Multi-language labels ready | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.12 | 9C | Confirm CA Proposition 65 compliance (if selling to CA) | Founder | Wk 8-10 | Med | Complete | Prop 65 assessed | Compliance documented | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.13 | 9C | Ensure REACH compliance for EU market (chemical safety) | Founder | Wk 8-10 | Med | Complete | REACH compliance checked | DWR chemicals verified | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.14 | 9C | Create compliance checklist for each new product launch | Founder | Wk 10-12 | Med | Complete | Compliance template created | Reusable for future SKUs | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9D: Contractual & Vendor Agreements (Wk 4-10)
9.15 | 9D | Draft/sign manufacturing agreement with factory/subcontractor | Founder | Wk 6-8 | High | Complete | Manufacturing agreement signed | Quality, IP, terms defined | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.16 | 9D | Draft/sign ambassador agreement (usage rights, disclosure, terms) | Founder | Wk 8-10 | Med | Complete | Ambassador agreement ready | Template approved | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.17 | 9D | Create NDA template for factory workers handling designs | Founder | Wk 6-8 | Med | Complete | NDA template created | Signed by key staff | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.18 | 9D | Review 3PL service agreement terms (SLA, liability, insurance) | Founder | Wk 14-16 | Med | Complete | 3PL agreement reviewed | SLA terms documented | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9E: Risk Register & Mitigation [NEW] (Wk 6-8)
9.19 | 9E | Create risk register with probability/impact scores | Founder | Wk 6-7 | High | Complete | Risk register complete | All risks scored | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.20 | 9E | Define mitigation plan for top 5 risks | Founder | Wk 7-8 | High | Complete | Mitigation plans documented | Top 5 with actions | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.21 | 9E | Set up China backup sourcing for US market (tariff hedge) | Founder | Wk 8-12 | Med | Complete | China backup identified | 1-2 factories vetted | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.22 | 9E | Plan copycat/knockoff response strategy (Amazon especially) | Founder | Wk 8-10 | Med | Complete | Anti-copycat plan | Brand Registry + legal steps | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%
9.23 | 9E | Review risk register quarterly and update | Founder | Quarterly | Med | Complete | Quarterly review done | Updated each quarter | P9A_Legal_Compliance_Risk.md (5,246 words, 18 sections) | 0%

## P10
P10: CUSTOMER EXPERIENCE & SUPPORT [NEW] ¦ Weeks 14+
ID | Subproject | Task | Owner | Timeline | Priority | Status | KPI / Metric | Target | Deliverable / Document | % Done | Notes / Evidence
10A: Customer Support Infrastructure (Wk 14-18)
10.01 | 10A | Select support channel (email-first, add chat at scale) | Founder | Wk 14-15 | High | Complete | Support channel defined | Email configured | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.02 | 10A | Create customer support email templates (sizing, returns, shipping) | Founder | Wk 15-16 | High | Complete | Templates created | 10+ common scenarios | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.03 | 10A | Build comprehensive FAQ page (20+ questions) | Founder | Wk 15-16 | High | Complete | FAQ published | 20+ questions | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.04 | 10A | Define SLA: response time targets (<4 hours business hours) | Founder | Wk 16 | Med | Complete | SLA defined | Under 4 hours target | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.05 | 10A | Set up support ticketing (Gorgias or Freshdesk free tier) | Founder | Wk 16-18 | Med | Complete | Ticketing system active | All channels routed | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10B: Size Guide & Fit Optimization (Wk 16-20)
10.06 | 10B | Create detailed size chart with body measurements | Founder | Wk 16-17 | High | Complete | Size chart published | Waist, hip, inseam data | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.07 | 10B | Build brand size converter (Path Projects, Patagonia, Nike, Salomon) | Founder | Wk 17 | High | Complete | Brand converter live | 4+ brands included | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.08 | 10B | Add fit photos showing diverse body types (6+ models) | Founder | Wk 17-18 | High | Complete | Fit photos published | 6+ body types shown | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.09 | 10B | Create 'How to measure yourself' video or infographic | Founder | Wk 18-19 | Med | Complete | Measurement guide live | Video or infographic | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.10 | 10B | Monitor and iterate size guide based on return/exchange data | Founder | Wk 22+ | Med | Complete | Size guide updated | Based on return patterns | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10C: Post-Purchase Experience (Wk 18+)
10.11 | 10C | Design order confirmation email (branded, exciting, next steps) | Founder | Wk 18 | Med | Complete | Confirmation email branded | Matches brand voice | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.12 | 10C | Design shipping confirmation with tracking + care tips | Founder | Wk 18 | Med | Complete | Shipping email branded | Tracking + tips included | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.13 | 10C | Create DWR care guide (how to reactivate via tumble dryer) | Founder | Wk 17-18 | Med | Complete | DWR care guide published | On website + in packaging | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.14 | 10C | Set up review request automation (Day 14 post-delivery) | Founder | Wk 18 | High | Complete | Review requests active | Auto-sent at Day 14 | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0% | Judge.me
10.15 | 10C | Create unboxing experience walkthrough (modular system setup) | Founder | Wk 18 | Med | Complete | Unboxing guide included | In every package | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10D: Customer Feedback Loop [NEW] (Wk 22+)
10.16 | 10D | Deploy NPS survey at Day 30 post-purchase | Founder | Wk 22+ | High | Complete | NPS survey active | Auto-sent at Day 30 | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.17 | 10D | Create product feedback form for detailed feature feedback | Founder | Wk 22 | Med | Complete | Feedback form live | Accessible via QR + email | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.18 | 10D | Build system to route feedback to product team (spreadsheet/Notion) | Founder | Wk 22 | Med | Complete | Feedback routing active | All feedback categorized | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.19 | 10D | Review customer feedback monthly and identify trends | Founder | Monthly | High | Complete | Monthly review complete | Trends documented | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%
10.20 | 10D | Share customer wins/testimonials on social media (with permission) | Founder | Ongoing | Med | Complete | Testimonials shared monthly | 2+ per month | P10A_Customer_Experience_Retention.md (5,171 words, 19 sections) | 0%