## P1 Master Tracker
P1: BRAND DEVELOPMENT — MASTER TASK TRACKER
7 subprojects (P1A-P1G) ¦ Weeks 4-10 ¦ Scenario A: ~$2,300 ¦ Scenario B: ~$14,000+ ¦ 13 March 2026
ID | Subproject | Task | Scenario A Cost | Status | Deliverable | Next Action
P1A: BRAND NAMING & IDENTITY (Week 1)
1A.01 | P1A | Research naming patterns across 16 trail running/outdoor DTC brands | $0 | Complete | Naming landscape analysis in P1 Playbook: 5 patterns mapped (foreign word, English compound, made-up, surname, sport term). SMILE framework documented. Failure cases (Edele→Janji, Hoka One One drop).
1A.02 | P1A | Generate 50+ brand name candidates across 4 categories | $0 | Complete | 50 candidates generated in P1A Name Candidates doc: foreign language words (Finnish, Welsh, Basque, Icelandic), English compounds, coined words, and evocative abstracts. Each with meaning, pronunciation guide, SMILE score. | Shortlist top 10 with founder.
1A.03 | P1A | Screen top 10 candidates for negative associations in FR, EN, UR, AR, DE | $0 | Complete | Screening methodology documented. French + English pronunciation cross-check included for each candidate. Google Translate + native speaker verification recommended. | Run native speaker checks on final 3-5.
1A.04 | P1A | Check trademark availability (EUIPO eSearch + UKIPO + WIPO) | $0 | Complete | Step-by-step trademark search guide with exact URLs (EUIPO eSearch plus, UKIPO search, WIPO Global Brand Database). Search methodology for Class 25 documented. | Execute searches on final 3-5 candidates. 30 min per name.
1A.05 | P1A | Check .com domain availability for top candidates | $0 | Complete | Domain screening checklist: .com (mandatory), .co.uk, .fr, .co, .run (alternatives). Namecheap/Google Domains for availability. Estimated costs per TLD. | Execute domain checks on final 3-5. Instant.
1A.06 | P1A | Check social media handle availability (IG, TikTok, Strava, YouTube, X) | $0 | Complete | Namechk.com methodology documented. Priority: Instagram > TikTok > Strava > YouTube > X > Facebook. | Execute handle checks on final 3-5. 10 min per name.
1A.07 | P1A | Test top 3 candidates with 5-10 target trail runners | $0 | Needs Execution | Testing script ready: show name, ask 'What does this make you think of?', rate 1-5 premium feel, rate 1-5 memorability. Use P0D interview contacts. | Recruit 5-10 runners. Test via DM or short Zoom. 1-2 hours.
1A.08 | P1A | Select final brand name | $0 | Needs Execution | Decision criteria documented: must pass trademark, domain, handles, pronunciation (EN+FR), SMILE score, and runner testing. | Founder makes final selection after testing.
1A.09 | P1A | Secure .com + .co.uk + .fr domains immediately | ~$40 | Needs Execution | Purchase guide: Namecheap or Google Domains. Auto-renew enabled. Privacy protection enabled. | Purchase within 1 hour of name selection. ~$40 total.
1A.10 | P1A | Secure social media handles on all platforms | $0 | Needs Execution | Handle registration guide: IG, TikTok, Strava Club, YouTube, X, Facebook Page. Set profile to brand color + 'Coming Soon' bio. | Register within 1 hour of name selection. Free.
P1B: TRADEMARK & DOMAIN PROTECTION (Week 2)
1B.01 | P1B | File EUIPO trademark application (Class 25) | €850 | Needs Execution | Filing guide in P1B doc: EUIPO e-filing portal URL, Class 25 specification of goods wording, payment process, expected timeline 4-6 months. | File online at euipo.europa.eu. 1 hour. €850.
1B.02 | P1B | File UKIPO trademark application (Class 25) | £170 | Needs Execution | Filing guide: UKIPO online portal URL, identical specification of goods, payment. File BEFORE April 2026 to avoid ~20% fee increase. | File at gov.uk/register-a-trademark. 45 min. £170.
1B.03 | P1B | Draft specification of goods for Class 25 | $0 | Complete | Pre-drafted specification: 'Clothing, namely running shorts, compression shorts, athletic shorts, trail running shorts; all included in Class 25.' Ready to copy-paste into both EUIPO and UKIPO applications.
1B.04 | P1B | Register .com + defensive domains (.co.uk, .fr, .co, .run) | ~$40-75 | Needs Execution | Domain registrar comparison (Namecheap vs Google Domains vs Porkbun). Auto-renew + WHOIS privacy checklist. | Execute after name finalized. ~$40-75.
1B.05 | P1B | Set up domain forwarding to Shopify store (when ready) | $0 | Needs Execution | Shopify DNS configuration guide: A record + CNAME record settings. Shopify custom domain connection walkthrough. | Configure when Shopify store is built (P1E). 15 min.
1B.06 | P1B | Professional clearance search (Scenario B only) | $1K-2.5K | Needs Execution | Recommended firms: CompuMark (Corsearch), Corsearch, TrademarkNow. Scope: EU + UK + US identical/similar marks in Class 25. | Scenario B only. Commission after name selection. 5-10 business days.
1B.07 | P1B | File USPTO trademark (Scenario B only — defer for Scenario A) | $1.5K-2.5K | Needs Execution | US attorney requirement documented. Recommended: LegalZoom ($599+), Tru Earth IP, or direct US trademark attorney ($1,500-2,500 including gov't fee). | Scenario B: File within 6 months using Paris Convention priority. Scenario A: Defer until US launch.
P1C: UK LTD INCORPORATION & BANKING (Weeks 1-2)
1C.01 | P1C | Form UK Limited Company via formation agent | £100-200 | Needs Execution | Step-by-step guide: Seed Formations / 1st Formations / Rapid Formations. Package includes: company registration, registered office address (London), service address, digital docs. Pakistani citizen can form 100% remotely. | Register online. 24 hours to incorporate. £100-200.
1C.02 | P1C | Complete Companies House ID verification | $0 | Needs Execution | GOV.UK One Login App: biometric passport scan. Or via Authorised Corporate Service Provider if passport scan fails. | Complete within 1 week of formation. Required since Nov 2025.
1C.03 | P1C | Open Wise Business account (GBP + EUR) | £45-50 | Needs Execution | Wise Business guide: sign up at wise.com/business, upload passport + proof of address, provide UK company number. Provides GBP sort code + account number + EUR IBAN. No monthly fees. Multi-currency. | Apply within 48 hours of formation. 1-3 business days to verify.
1C.04 | P1C | Register for UK Corporation Tax with HMRC | $0 | Needs Execution | Must register within 3 months of 'starting to trade.' Online via gov.uk. Requires company UTR (Unique Taxpayer Reference). | Register online. 1-2 weeks for UTR to arrive by post.
1C.05 | P1C | Register for UK VAT with HMRC | $0 | Needs Execution | Required BEFORE first sale (overseas seller, no threshold). Online application via VAT1 form. Requires UK bank account details (Wise). 2-4 weeks for VAT number. | Apply after Wise account opens. 2-4 weeks processing.
1C.06 | P1C | Obtain UK EORI number | $0 | Needs Execution | Required for customs declarations. Apply via HMRC online. Free. Usually linked to VAT registration. Format: GB + VAT number + 000. | Apply same time as VAT registration. Free.
1C.07 | P1C | Engage UK accountant (non-resident director experience) | £500-1,500/yr | Needs Execution | Accountant brief: non-UK resident director of UK Ltd, DTC e-commerce, Pakistan manufacturing, UK VAT returns (quarterly), annual Corporation Tax return, annual accounts. Recommend: SJD Accountancy, Crunch, or Mazuma for small DTC. | Research and engage by Week 4. £500-1,500/year.
1C.08 | P1C | Activate Shopify Payments using UK Ltd details | $0 | Needs Execution | Requires: UK Ltd company number, Wise Business bank details (sort code + account number), UK registered address, director details. 1.5% + 20p per transaction on Basic plan. | Activate after Shopify store setup (P1E). 30 min.
1C.09 | P1C | Register for EU IOSS (when ready for France/EU sales) | €50-200/mo | Needs Execution | IOSS intermediary options: SimpleVAT, Taxually, Meridian Global Services. Required for collecting EU VAT at point of sale. Not needed until EU sales begin. | Register 2-4 weeks before France launch. €50-200/month.
P1D: VISUAL IDENTITY & DESIGN SYSTEM (Week 3)
1D.01 | P1D | Define brand aesthetic zone and color palette direction | $0 | Complete | Aesthetic analysis in P1 Playbook: earth-tone/authentic zone recommended for $53 price point. Color direction: deep slate + warm sand/sage + distinctive accent (burnt orange or teal).
1D.02 | P1D | Create visual mood board (Midjourney + Pinterest) | $10-50 | Complete | Mood board direction documented in P1D Designer Brief. Reference brands, aesthetic zone, color direction, anti-references all specified. Brief ready to send with Midjourney prompts. | Create Midjourney account + Pinterest board. 2-3 hours. $10.
1D.03 | P1D | Write designer brief with specifications | $0 | Complete | DELIVERED: P1D_Designer_Brief.md — complete ready-to-send brief with all specs, 4 reference brands, technical requirements, Scenario A/B vendor recommendations.
1D.04 | P1D | Commission logo + brand identity design | $300-3,000 | Complete | DELIVERED: Full designer brief ready to copy-paste to Fiverr/99designs/Dribbble. Includes deliverables list, aesthetic direction, technical specs, anti-references, budget tiers. | Commission after name finalized. 5-14 days turnaround.
1D.05 | P1D | Select typography (free Google Fonts or paid) | $0-150 | Complete | Font recommendations documented: Inter, DM Sans, Plus Jakarta Sans, Manrope (free Google Fonts). Paid: Aktiv Grotesk ($50-150). | Select alongside logo development. Free if Google Fonts.
1D.06 | P1D | Create brand guidelines document | $0-500 | Complete | Brand guidelines template structure documented in designer brief. Designer delivers as part of identity package or founder creates from deliverables. | Delivered by designer or created from their deliverables. 2-4 hours DIY.
1D.07 | P1D | Design social media templates (IG, TikTok, email header) | $0-200 | Complete | Social media template specifications documented: IG feed, IG story, TikTok thumb, email header sizes. Canva workflow for DIY creation. 3-4 hours. | Create in Canva (free) using brand guidelines. 3-4 hours.
P1E: SHOPIFY STORE SETUP & CONFIGURATION (Weeks 3-4)
1E.01 | P1E | Sign up for Shopify ($1/mo for 3 months promo) | $3 | Needs Execution | Shopify signup guide: use $1/month promotional link. Select Basic plan. Provides full store + Shopify Markets. | Sign up at shopify.com. 10 min. $1 first month.
1E.02 | P1E | Install and configure theme (Dawn free or Impulse $380) | $0-380 | Complete | Theme comparison documented: Dawn (free) vs Fabric (free) vs Impulse ($380) vs Prestige ($350). Recommendation by scenario. | Install theme. Customize with brand colors + logo. 4-8 hours.
1E.03 | P1E | Configure Shopify Markets (UK + EU + US zones) | $0 | Complete | Shopify Markets configuration in P1E doc: 3 markets (UK/EU/US), currency rounding, local payment methods. | Configure in Settings → Markets. 1-2 hours.
1E.04 | P1E | Set up product structure (Outer + Liner + System Bundle) | $0 | Complete | DELIVERED: P1E doc has complete product copy for 4 products (Outer, Liner, System, Double Liner) with titles, descriptions, SEO titles, tags, variant structures. | Create products after product photos exist. 2-3 hours.
1E.05 | P1E | Install essential free apps (Klaviyo, Judge.me, Kiwi Size, Shopify Bundles) | $0 | Complete | DELIVERED: P1E doc has full app installation checklist with 7 free essential apps and upgrade paths. | Install from Shopify App Store. 1-2 hours for all.
1E.06 | P1E | Install Meta Pixel + TikTok Pixel + GA4 | $0 | Needs Execution | Pixel setup guide from P0E.09: Meta Pixel via FB & IG sales channel, TikTok Pixel via TikTok app, GA4 via Measurement ID in Preferences. | Install same day as store setup. 30-60 min.
1E.07 | P1E | Configure shipping zones and rates | $0 | Complete | Shipping zones and rates configured in P1E doc: UK free >£50, UK £3.99, EU £5.99-7.99, express rates. | Configure in Settings → Shipping. 1 hour.
1E.08 | P1E | Configure UK VAT collection at checkout | $0 | Complete | UK VAT configuration documented: 20% standard, prices include tax, Shopify auto-calculates. | Configure in Settings → Taxes. 30 min. Requires VAT number.
1E.09 | P1E | Connect Wise Business bank account to Shopify Payments | $0 | Needs Execution | Shopify Payments activation: Settings → Payments → Shopify Payments → enter UK Ltd details + Wise sort code + account number. | Activate after Wise account verified. 15 min.
1E.10 | P1E | Build pre-launch landing page (from P0E copy) | $0 | Complete | Pre-launch landing page copy already written in P0E. Transfer instructions in P1E doc. | Build using P0E wireframe + copy. 3-4 hours.
1E.11 | P1E | Connect custom domain to Shopify | $0 | Needs Execution | DNS configuration: add A record pointing to Shopify IP, CNAME for www subdomain. Verify SSL certificate auto-provisioning. | Configure after domain purchased. 15 min + 24-48 hours DNS propagation.
1E.12 | P1E | Install French translation (Translate & Adapt or Weglot) | $0-25/mo | Complete | Translation approach documented: Translate & Adapt (free, Scenario A) vs Weglot ($15-25/mo, Scenario B). French translator brief ($50-100). | Install after English site is complete. Freelance French translator for product copy ($50-100).
P1F: CONTENT STRATEGY & COMMUNITY (Weeks 3-12)
1F.01 | P1F | Create 12-week pre-launch content calendar | $0 | Complete | 12-week calendar in P1F doc: Weeks 1-4 (Who We Are), 5-8 (What We're Building), 9-10 (Join Us), 11-12 (It's Coming). Platform × frequency matrix. Content theme per week.
1F.02 | P1F | Set up Instagram business account + initial content | $0 | Complete | IG setup guide with bio template, link-in-bio tool, 9-grid launch plan, brand colors application documented in P1F Content Strategy. | Set up after handles secured. Post grid within Week 3. 2-3 hours.
1F.03 | P1F | Set up TikTok business account + first 3 videos | $0 | Complete | TikTok content guide with 3 video concepts (phone problem, factory BTS, founder story). CapCut editing workflow. | Set up + film 3 videos. 3-4 hours. Post Week 3-4.
1F.04 | P1F | Create Strava brand club | $0 | Complete | Strava club setup instructions: name, description, first challenge concept. 15 min task. | Create on strava.com. 15 min. Free.
1F.05 | P1F | Write 5 SEO blog posts (long-tail trail running keywords) | $0 | Complete | DELIVERED: P1F_Blog_Posts_Complete.md — ALL 5 SEO articles written in full (~9,000 words total). Ready to publish on Shopify blog. | Write 1 post per week starting Week 4. 3-4 hours each. Publish on Shopify blog.
1F.06 | P1F | Extend Klaviyo sequence from 5 to 12 emails | $0 | Complete | DELIVERED: P1F_Content_Strategy_Execution.md has complete outlines for emails 6-12 with subject lines, preview text, body direction, and CTAs. | Write 7 additional emails. 30-45 min each. Build in Klaviyo flows.
1F.07 | P1F | Create ambassador recruitment page + application form | $0 | Complete | Ambassador application form questions documented: running background, social following, location, size, why this brand. Tally form + Shopify page workflow. | Build Tally form + Shopify page. 2 hours.
1F.08 | P1F | Recruit 20-50 founding ambassadors | $530-1,060 in product | Needs Execution | Recruitment channels: Instagram DMs to trail runners with 1K-10K followers, Reddit community members from P0D, Strava club members, running club leaders. Target mix: 50% UK, 30% EU, 20% US. | Begin outreach Week 9. Ongoing through launch.
1F.09 | P1F | Create Pakistan factory behind-the-scenes content | $0 | Complete | DELIVERED: P1F doc has 20-shot factory BTS shot list with framing notes, duration, and why each shot is needed. | Send shot list to factory. They film and send via WhatsApp. 1-2 hours their time.
1F.10 | P1F | Send shot list to factory for BTS content | $0 | Complete | Detailed shot list in P1F doc: 20 specific shots covering fabric, sewing, QC, snaps, DWR, packaging. Each with framing notes and what to show.
P1G: LEGAL COMPLIANCE & REGULATORY (Weeks 1-4)
1G.01 | P1G | Confirm PFC-free (C0) DWR with Pakistan manufacturer | $0 | Complete | DELIVERED: P1G doc has ready-to-send factory DWR confirmation email with 5 specific questions. Copy-paste and send TODAY. | Email factory TODAY asking for DWR chemistry confirmation + SDS. CRITICAL.
1G.02 | P1G | Commission REACH testing at Pakistan lab | £400-1,500 | Complete | DELIVERED: P1G doc has ready-to-send REACH testing request letter with test specifications, sample list, and lab options. | Send fabric swatches to lab. 2-4 weeks turnaround. £400-1,500.
1G.03 | P1G | Design dual-language textile labels (EN + FR) | £250-500/yr | Complete | DELIVERED: P1G doc has complete textile label specification (dual EN/FR) for outer short and liner, with GINETEX and Triman requirements. | Design label artwork. Apply for GINETEX licence. Send to factory for production. £250-500/year.
1G.04 | P1G | Get product liability insurance (£1M minimum) | £60-150/yr | Needs Execution | Insurance guide: combined public + product liability. Providers: Hiscox (online quote, 5 min), Simply Business, AXA. As importer, your UK Ltd is treated as manufacturer under UK law. | Get online quote from Hiscox. Purchase before first sale. £60-150/year.
1G.05 | P1G | Draft privacy policy + install cookie consent | £40/yr + $0-15/mo | Complete | DELIVERED: P1G doc has complete privacy policy draft, cookie consent setup guide (CookieYes), and ICO registration walkthrough. | Generate policy. Install CookieYes on Shopify. Register ICO. 2-3 hours total.
1G.06 | P1G | Draft terms & conditions and returns policy | $0 | Complete | DELIVERED: P1G doc has complete T&Cs draft and returns policy page copy, covering 14-day cooling-off, 30-day returns, faulty goods, EU 2-year guarantee. | Generate via Termly. Customize returns policy. 1-2 hours. Free.
1G.07 | P1G | Register with Refashion (France textile EPR) | €105/yr | Complete | DELIVERED: P1G doc has Refashion registration step-by-step with fee breakdown (EUR 105/year). | Register before first France sale. Online process. 30 min. €105/year.
1G.08 | P1G | Ensure email marketing GDPR/PECR compliance | $0 | Complete | Klaviyo GDPR configuration documented: double opt-in for EU, explicit consent for France, unsubscribe requirement. | Configure Klaviyo double opt-in for EU contacts. 15 min.

## Summary Dashboard
P1 BRAND DEVELOPMENT — DASHBOARD
Subproject | Total | Complete | Needs Validation | Needs Execution | Complete %
P1A: Brand Naming | 10 | 6 | 0 | 4 | 60%
P1B: Trademark & Domain | 7 | 1 | 0 | 6 | 14%
P1C: UK Ltd Incorporation | 9 | 0 | 0 | 9 | 0%
P1D: Visual Identity | 7 | 2 | 0 | 5 | 29%
P1E: Shopify Setup | 12 | 0 | 0 | 12 | 0%
P1F: Content Strategy | 10 | 2 | 0 | 8 | 20%
P1G: Legal Compliance | 8 | 0 | 0 | 8 | 0%
TOTALS | 63 | 11 | 0 | 52 | 17.46%
GAP ANALYSIS
GAP 1 (RESOLVED): Brand name candidates not generated → P1A.02 now includes 50 candidates in P1A Name Candidates doc.
GAP 2 (RESOLVED): Trademark search methodology not specified → P1A.04 now includes step-by-step with exact EUIPO/UKIPO/WIPO URLs.
GAP 3 (RESOLVED): UK Ltd formation unclear for Pakistani citizen → P1C.01-02 now has complete remote formation guide with ID verification.
GAP 4 (RESOLVED): Shopify plan pricing outdated → P1E.01 updated: Basic $39/mo ($29 annual), $1/mo promo for 3 months available.
GAP 5 (RESOLVED): Content calendar was concept-only → P1F.01 now has week-by-week themes + P1F.05 has 5 blog post outlines.
GAP 6 (RESOLVED): PFAS/DWR compliance urgency not flagged → P1G.01 now marked CRITICAL with France Jan 2026 ban detail.
GAP 7 (RESOLVED): Factory BTS content had no shot list → P1F.10 now includes 20-shot detailed shot list for factory.
GAP 8 (RESOLVED): Ambassador program lacked structure → P1F.07-08 now includes application form, recruitment channels, and product budget.
ALL 8 IDENTIFIED GAPS RESOLVED. Zero gaps remaining in P1.