## 30-Day Task Sheet
FOUNDER'S 30-DAY TASK SHEET — The Forgotten Front Monetization Roadmap
Day | Track | Project | Sub-Proj | Task | Detailed Instructions | Time | Deliverable | Dependency | Done?
══════ DAY 1 ══════
1 | SETUP | — | — | Create KDP account | Go to kdp.amazon.com → Sign in with Amazon → Complete account setup → Start W-8BEN tax interview (Pakistan → 0% withholding if treaty applies) → Add bank/payment details. You'll need: passport, bank account IBAN, address. | 20 min | KDP account active | None | ☐
1 | SETUP | — | — | Create Canva account | Sign up at canva.com (free tier). Upload brand fonts: Oswald (titles), Libre Baskerville (subtitles), Special Elite (stamps), Outfit (body), Playfair Display (KDP Dad niche), Bebas Neue (KDP Running niche). Create brand kit with 6 YouTube colors + 3 KDP color schemes. | 15 min | Canva account with fonts | None | ☐
1 | SETUP | — | — | Create YouTube channel | Sign into YouTube → Create channel → Set handle to @TheForgottenFront → Upload profile picture (TFF logo from Y1.3) → Upload banner image → Fill About section with channel description from Y1.3 → Add links to future Instagram/website → Set channel country → Enable monetization eligibility notifications. | 15 min | YouTube channel live | None | ☐
1 | SETUP | — | — | Create Instagram account | Download Instagram → Create account @theforgottenfront → Switch to Professional Creator account → Set category 'Education' → Write bio (Version A from I1.1) → Upload profile picture (same TFF logo) → Add YouTube channel link in bio → Enable search engine indexing in Privacy settings → Ensure account is Public. | 10 min | Instagram profile live | I1.1 guide | ☐
1 | SETUP | — | — | Register handles on other platforms | Create @TheForgottenFront on: TikTok, Twitter/X, Threads. Create theforgottenfront@gmail.com (dedicated brand email). Add this email as Instagram contact button. Claim handles even if you won't use platforms immediately. | 15 min | All handles claimed | None | ☐
1 | SETUP | — | — | Install production tools | Install Audacity (free, audacityteam.org) for voiceover recording. Install CapCut (free, desktop version) for video editing. Create folder structure on computer: TheForgottenFront/ → Scripts/, Assets/, Audio/, Exports/, Thumbnails/, Instagram/, TikTok/, Brand/. Download YouTube Audio Library tracks for background music. | 15 min | Tools installed + folders ready | None | ☐
1 | SETUP | — | — | Create link-in-bio page | Sign up at beacons.ai → Create page for @theforgottenfront → Add links: YouTube channel (with ?sub_confirmation=1), 'About The Forgotten Front' → Customize colors: dark background #0A0A0A, amber accents #D97706 → Copy Beacons URL → Update Instagram bio with Beacons link. | 10 min | Beacons page live | Instagram account | ☐
══════ DAY 2 ══════
2 | KDP | K2 | K2.3 | Book 1 interior — structure setup | Open Canva → Custom Size 6×9 inches (432×648px) → Create title page: 'The New Dad Journal: Your First Year of Fatherhood' in Playfair Display, navy (#1E3A5F) on cream (#FDF8F0) → Copyright page with pen name from K1.3 → Table of contents (12 monthly sections + 4 bonus sections) → Introduction page (500 words, warm tone, from new dad to new dad). | 45 min | Book 1 pages 1-6 | KDP account + Canva | ☐
2 | KDP | K2 | K2.3 | Book 1 interior — Months 1-4 | Build each monthly section per K2.1 specs: Monthly milestone checklist (8-10 items per month like 'First smile', 'First roll over'), Guided journal prompts (5 per month: 'What surprised you most this month?', 'A moment you want to remember forever'), Photo spot placeholder (framed empty space with 'Paste photo here'), Sleep tracker grid (7×4 weekly grid), Feeding log template. Use cream background, navy text, amber (#D97706) accent lines. | 60 min | Book 1 pages 7-46 | Day 2 structure | ☐
2 | INSTAGRAM | I1 | I1.2 | Create 5 Story Highlight covers | Open Canva → 1080×1920px → Dark background #0A0A0A → For each cover: place a simple amber (#D97706) line icon centered (search Canva Icons for: book, play button, lightbulb, magnifying glass, stack of books) → Export 5 images as PNG → Upload each as an Instagram Story → Add to respective Highlights: ABOUT, LATEST, FACTS, RESEARCH, BOOKS. | 10 min | 5 branded Highlight covers | Instagram account | ☐
══════ DAY 3 ══════
3 | KDP | K2 | K2.3 | Book 1 interior — Months 5-12 | Continue building monthly sections for Months 5-12. Each month follows same template: milestone checklist + journal prompts + photo spot + trackers. Adjust milestones per age (Month 5: sitting up, Month 8: crawling, Month 10: first words, Month 12: first steps). Add 'Daddy's Favorites This Month' reflection box to each month. Maintain consistent formatting. | 90 min | Book 1 pages 47-110 | Day 2 pages | ☐
3 | KDP | K2 | K2.3 | Book 1 interior — bonus sections + final | Build 4 bonus sections: 'Letter to My Baby' (2 lined pages), 'Emergency Contacts' (structured form), 'Baby's Firsts Tracker' (2-page checklist of 50+ firsts), 'Notes & Memories' (10 lined pages). Add back matter: blank page + 'More journals at [Amazon author page URL]'. Final count: ~120 pages. Review entire interior for consistency. | 40 min | Book 1 interior complete | Day 3 months | ☐
3 | INSTAGRAM | I1 | I1.2 | Create 4 Instagram Canva templates | Build per I1.2 specs: Template 1 — Reel Cover (1080×1920, dark bg, Oswald title, red badge, amber bar, watermark). Template 2 — Carousel (1080×1350, 8-page: hook+5 facts+summary+CTA). Template 3 — Fact Card (1080×1350, dark bg, Libre Baskerville quote, amber accent). Template 4 — Story (1080×1920, 3 variants: fact/poll/teaser with safe zones marked). Save each as separate Canva design. | 45 min | 4 reusable Canva templates | I1.2 guide | ☐
══════ DAY 4 ══════
4 | KDP | K2 | K2.3 | Book 1 cover — front design | Go to kdp.amazon.com/cover-calculator → Input: 6×9 trim, 120 pages, B&W interior, white paper → Download cover template PDF with spine measurements → Open Canva Custom Size matching template dimensions → Design front cover per K2.2 Dad Niche blueprint: cream background #FDF8F0, navy title in Playfair Display Bold, amber rule line, subtitle in Outfit Light, pen name at bottom. Keep text within safe margins (0.25" from trim). | 30 min | Front cover designed | Book 1 interior | ☐
4 | KDP | K2 | K2.3 | Book 1 cover — spine + back + export | Design spine: navy background, book title in Playfair Display (calculate font size from K2.2 spine calculator: 120 pages × 0.002252" = 0.27" spine width → use 7-8pt font). Design back cover: cream background, 150-word description, barcode placement zone (bottom right, DO NOT place any content there), pen name, 'Printed in USA'. Export full cover as PDF Print (flatten, no crops). Export ebook cover separately as 2560×1600 JPEG. | 30 min | Complete cover PDF + ebook cover | Front cover | ☐
4 | KDP | K2 | K2.3 | Book 1 interior — final review + export | Review entire Book 1 interior in Canva: check all margins are safe (0.5" inner, 0.25" outer for 6×9), verify page count is even, check font consistency across all pages, ensure no text touches edges, verify cream background is uniform. Export as PDF Print (highest quality, flatten). Check exported PDF: open in PDF viewer, scroll through every page, verify nothing is cut off. | 20 min | Book 1 interior PDF ready | Book 1 complete | ☐
══════ DAY 5 ══════
5 | KDP | K2 | K2.4 | PUBLISH Book 1 on Amazon KDP 🎉 | Log into KDP → Paperback → Create: Title 'The New Dad Journal', subtitle 'A Guided First-Year Journal for New Fathers', pen name from K1.3, description (use K1.4 template: benefit-driven, 4000 chars max, HTML bold allowed), 7 backend keywords from K1.4 (e.g., 'new dad gift journal first year fatherhood'), select 3 BISAC categories from K1.4 mapping. Upload interior PDF + cover PDF. Set trim 6×9, no bleed, white paper, B&W ink. Price: $12.99 (60% royalty = $5.09/copy). Enable expanded distribution. Preview entire book in KDP previewer — check every page. Submit. | 40 min | Book 1 submitted to KDP review | Cover + interior PDFs | ☐
5 | KDP | K2 | K2.4 | Book 1 — ebook version setup | In KDP dashboard → Create Kindle eBook for same title. Upload ebook cover (2560×1600). For interior: export Canva pages as high-quality images → convert to reflowable format using Kindle Create (free tool) OR upload as fixed-layout PDF. Set ebook price $4.99 (70% royalty in most territories). Link paperback and ebook editions. Submit. | 25 min | Ebook submitted to KDP | Book 1 paperback submitted | ☐
5 | INSTAGRAM | I1 | I1.1 | Create 'ABOUT' highlight Stories | Create 3-5 Stories for your ABOUT highlight: Story 1 — 'What is The Forgotten Front?' (dark background, Oswald title, 2-line explanation). Story 2 — 'What you'll learn here' (list: untold battles, forgotten soldiers, secret operations). Story 3 — 'New stories every Tuesday & Thursday' (posting schedule). Story 4 — 'Full documentaries on YouTube ↓' (with link sticker to channel). Post each as Story → Add all to ABOUT highlight. | 15 min | ABOUT highlight populated | IG templates + account | ☐
══════ DAY 6 ══════
6 | YOUTUBE | Y2 | Y2.1 | Video #1 — research phase | Topic: 'The 2.5 Million Soldiers History Forgot — India in WW2'. Use Claude prompt from Y2.1: 'Research the role of Indian soldiers in World War 2. Include: total numbers, key theaters (Burma, North Africa, Italy, Middle East), major battles (Imphal, Kohima, Monte Cassino), casualties, political context (independence movement vs war service), post-war treatment.' Compile 15-20 key facts. Identify 3 emotional hooks. Note all statistics with sources for accuracy. | 45 min | Research document with 15+ facts | None | ☐
6 | YOUTUBE | Y2 | Y2.1 | Video #1 — script writing | Write full script (~2,100 words for 12-15 min video) using Y2.1 3-Act Structure: Act 1 HOOK (first 30 seconds — the shocking stat: '2.5 million men volunteered...'), Act 2 BODY (chronological narrative: recruitment → training → Burma campaign → Imphal/Kohima → Italy → aftermath), Act 3 CLOSE (emotional landing: 'They fought for an empire that wouldn't free them'). Add [VISUAL CUE] markers every 15-20 seconds. Rewrite 40-60% in your own voice — remove AI-sounding phrases. | 60 min | Complete video script with visual cues | Research document | ☐
6 | YOUTUBE | Y2 | Y2.2 | Video #1 — visual asset collection | Download 20+ archival images from copyright-safe sources per Y2.2: Imperial War Museum (iwm.org.uk — Crown Copyright, free for editorial use), Library of Congress (loc.gov/pictures — PD), Wikimedia Commons (search 'Indian Army WW2' — verify PD tag), National Archives of India. Download 2-3 maps (Burma campaign, Imphal region). Save all in TheForgottenFront/Assets/V001/ with descriptive filenames. | 30 min | 20+ archival images + maps | Script (to know what visuals needed) | ☐
6 | YOUTUBE | Y3 | Y3.3 | Video #1 — keyword research | YouTube autocomplete: type 'Indian army WW2' and note all suggestions. Type 'forgotten soldiers', 'Imphal battle', 'India World War 2'. Use TubeBuddy/VidIQ free tier to check search volume and competition for top 10 keyword phrases. Select: primary keyword for title, 5 tags, 3 hashtags. Draft title using Y3.3 formula (e.g., 'The 2.5 Million Soldiers History Forgot ¦ India in WW2'). | 15 min | Primary keyword + 5 tags + draft title | None | ☐
══════ DAY 7 ══════
7 | YOUTUBE | Y2 | Y2.3 | Video #1 — voiceover recording | Set up USB mic per Y2.3 (if no USB mic yet: use phone with voice recorder app — hold 6 inches from mouth, quiet room, no echo). Record in Audacity: set sample rate 44100Hz, mono. Read script naturally — conversational, not newscaster. Pause 2 seconds between sections for editing. Do 2 full takes. Apply Y2.3 7-step mastering chain: noise reduction → normalize → compress → EQ (cut below 80Hz, boost 2-4kHz) → normalize again → limiter → export as WAV. | 45 min | Mastered voiceover WAV file | Script + Audacity | ☐
7 | YOUTUBE | Y2 | Y2.2 | Video #1 — video editing | Open CapCut → Import voiceover + all visual assets. Build timeline: voiceover as primary audio track → layer images with Ken Burns effect (slow zoom/pan, 4-6 seconds per image) → add maps with animated arrows for troop movements → add text overlays for key stats/names/dates (Oswald Bold, white on dark overlay) → add background music from Pixabay Music (cinematic/documentary, volume at 15-20% of voice) → create outro sequence (subscribe + next video teaser). Target: clean 12-15 minute video. | 90 min | Complete video MP4 file | Voiceover + visual assets | ☐
7 | YOUTUBE | Y2 | Y2.4 | Video #1 — thumbnail creation | Open Canva → 1280×720px → Use Template A 'The Reveal' from Y2.4: dramatic archival image (Indian soldiers marching) as background with 40% dark overlay → large Oswald Bold text: '2.5 MILLION FORGOTTEN' in white → red badge 'UNTOLD' top-left → amber accent bar → channel watermark. Export as PNG. Check: is text readable at thumbnail size? Does it create curiosity? Would YOU click this? | 15 min | Thumbnail PNG file | Visual assets | ☐
7 | INSTAGRAM | I1 | I1.1 | Post 3 'About' Stories | Create and post 3 Stories using Story template from I1.2: 1) Archival photo + 'Stories begin next week' text, 2) Poll: 'Do you know how many Indian soldiers fought in WW2?' with options, 3) 'Follow for untold military history' CTA. These warm up the account before first feed post. | 10 min | 3 Stories posted | IG templates | ☐
══════ DAY 8 ══════
8 | YOUTUBE | Y3 | Y3.1 | PUBLISH Video #1 on YouTube 🎉 | Upload to YouTube Studio: select video file → add thumbnail → Title (from Day 6 keyword research) → Description (use Y3.3 template: hook paragraph, timestamps, 'About This Channel', social links, hashtags) → Tags (from keyword research) → Category: Education → Language: English → Subtitle upload if available → End screen (subscribe button + next video placeholder) → Cards (if applicable) → Visibility: Public → Publish. Pin comment: engagement question from script. | 20 min | Video #1 LIVE on YouTube | Video file + thumbnail | ☐
8 | YOUTUBE | Y3 | Y3.1 | Video #1 — create 3 Shorts | From Video #1, extract 3 Shorts per Y2Y3 Gap Analysis workflow: Short 1: the hook stat ('2.5 million soldiers...'), Short 2: most dramatic fact ('At Imphal, they held the line...'), Short 3: emotional close ('They fought for freedom — just not their own'). Each Short: 30-60 seconds, vertical 1080×1920 in CapCut, auto-captions ON, hook in first 0.5 seconds, Pixabay Music background. Export 3 files WITHOUT YouTube watermark. | 30 min | 3 Short MP4 files | Video #1 published | ☐
8 | YOUTUBE | Y3 | Y3.1 | Upload 3 Shorts to YouTube | Upload each Short to YouTube Studio: vertical format auto-detected → add #Shorts tag → write unique title for each (not same as long-form) → add description with channel link → category Education → Publish all 3. Space them: upload 1 now, schedule other 2 for Days 9 and 10. | 10 min | 3 Shorts live/scheduled on YouTube | 3 Short files | ☐
8 | INSTAGRAM | I1 | I1.4 | Cross-post Reel #1 + first feed content | Take Short #1 export from CapCut (no watermark!) → Create Reel cover in Canva (duplicate Template 1, swap title text) → Open Meta Business Suite → Upload video + custom cover → Write Instagram caption using I1.3 template (hook + context + CTA + 3-5 hashtags from Set 1: #TheForgottenFront #IndianMilitaryHistory #ForgottenSoldiers #HistoryNerd) → Schedule for 7 PM PKT. THIS IS YOUR FIRST INSTAGRAM FEED POST. | 10 min | First Instagram Reel published | Short #1 + IG templates | ☐
8 | YOUTUBE | Y3 | Y3.4 | Video #1 — promotion sprint | Share Video #1 to: r/IndianHistory (write genuine 3-sentence intro, don't spam), r/MilitaryHistory, r/history. Share to 2 Facebook groups (Military History, WW2 History). Write 1 Quora answer to a related question ('What role did India play in WW2?') with natural link to video. Post video link to Twitter/X with 3-sentence hook. Reply to EVERY comment on the YouTube video within first 24 hours. | 20 min | Video shared to 5+ communities | Video #1 live | ☐
══════ DAY 9 ══════
9 | INSTAGRAM | I1 | I1.4 | Instagram content blitz — Carousel + Reel + Fact Card | Carousel: Duplicate Template 2 → '5 Things You Didn't Know About the Indian Army in WW2' → Fill 5 fact slides from Video #1 research → Hook slide: large text, dark bg → CTA slide: 'Follow @theforgottenfront' → Schedule in Meta BS. Reel #2: Upload Short #2 from CapCut + Canva cover → caption + hashtags Set 1 → schedule. Fact Card: Duplicate Template 3 → '2.5 million Indians served in WW2 — the largest volunteer army in history' → schedule. Also upload Short #2 to TikTok with TikTok-native captions. | 25 min | Carousel + Reel + Fact Card scheduled | Shorts + templates + research | ☐
9 | KDP | K2 | K2.3 | Check Book 1 KDP status + order proof | Log into KDP dashboard. Book 1 should show 'In Review' or 'Live'. If Live: order author proof copy (takes 3-7 days to arrive — check physical quality). If 'Action Required': read the notification carefully, fix the issue (usually margin or image resolution), resubmit. Check listing on Amazon: search your exact title, verify it appears, check how the cover thumbnail looks. | 10 min | Book 1 status confirmed | Book 1 submitted | ☐
9 | YOUTUBE | Y3 | Y3.4 | Reply to all Video #1 comments | Check YouTube Studio → Comments. Reply to every single comment on Video #1. Be genuine, ask follow-up questions, heart good comments. This signals engagement to the algorithm. Check Reddit/Facebook posts for any responses and reply there too. | 10 min | All comments replied to | Video #1 promotion | ☐
══════ DAY 10 ══════
10 | YOUTUBE | Y2 | Y2.1 | Video #2 — research + script | Topic: 'The Battle That Saved India — Imphal 1944'. Research: Japanese Operation U-Go, Subhas Chandra Bose and INA, British-Indian defense, the siege, Kohima tennis court battle, the turning point, Japanese retreat and casualties (over 50,000 dead), significance for Indian independence. Write ~2,000 word script using 3-Act Structure. [VISUAL CUE] markers throughout. Self-edit: remove repetition, tighten pacing, strengthen hook. | 90 min | Video #2 script complete | None | ☐
10 | YOUTUBE | Y2 | Y2.2 | Video #2 — visual assets | Download 15-20 images: Imphal battlefield photos, Japanese army Burma, INA soldiers, Kohima War Cemetery, maps of the Imphal Plain. Sources: IWM, Australian War Memorial (good Burma campaign photos), Wikimedia. Create custom map in Canva showing Japanese advance routes toward Imphal. | 25 min | 15+ archival images + custom map | Script (visual needs) | ☐
10 | INSTAGRAM | I1 | I1.4 | Cross-post Reel #3 + daily Stories | Upload Short #3 as Instagram Reel with custom cover and I1.3 caption template. Post 2 Stories: archival photo with 'Did you know?' text overlay + poll ('Have you heard of the Battle of Imphal?'). Upload Short #3 to TikTok. | 10 min | Reel #3 + 2 Stories | Short #3 | ☐
══════ DAY 11 ══════
11 | YOUTUBE | Y2 | Y2.3 | Video #2 — record + master voiceover | Record Video #2 voiceover in Audacity. Apply Y2.3 mastering chain. Review: is pacing better than Video #1? Did you reduce 'um' and 'ah'? Is the emotional beat at the climax (Japanese retreat) hitting hard enough? Re-record the hook if needed — the first 15 seconds determine if people stay. | 40 min | Mastered voiceover #2 | Script #2 + Audacity | ☐
11 | YOUTUBE | Y2 | Y2.2 | Video #2 — edit in CapCut | Build Video #2 timeline in CapCut: voiceover → images with Ken Burns → custom maps with animated arrows (Japanese advance toward Imphal, then retreat) → text overlays for names/dates/stats → background music (more intense than V1 — this is a battle story) → outro. Aim for 12-15 minutes. Export 1080p MP4. | 80 min | Complete Video #2 MP4 | Voiceover + assets | ☐
11 | YOUTUBE | Y2 | Y2.4 | Video #2 — thumbnail | Canva 1280×720 → dramatic Imphal battlefield image → text 'THE BATTLE THAT SAVED INDIA' Oswald Bold → red 'FORGOTTEN' badge → amber bar. Test: readable at small size? Creates curiosity? | 12 min | Thumbnail #2 PNG | Visual assets | ☐
══════ DAY 12 ══════
12 | YOUTUBE | Y3 | Y3.1 | PUBLISH Video #2 + Shorts batch | Upload Video #2 → full Y3.3 metadata template → thumbnail → end screens → publish. Create 3 Shorts from Video #2 in CapCut (battle moments, shocking stats, emotional conclusion). Upload 1 Short now, schedule other 2 for Days 13-14. Promote: Reddit r/IndianHistory, r/MilitaryHistory + 2 Facebook groups + 1 Quora answer. | 45 min | Video #2 + 3 Shorts live/scheduled | Video #2 file | ☐
12 | KDP | K2 | K2.3 | Start Book 2 — E-Commerce Planner interior | Begin Book 2 (E-Commerce Business Planner, $12.99) in Canva 6×9. Build structure: title page → copyright → TOC → sections per K2.1 specs: Business Model Canvas (2 pages), Revenue Tracker (monthly, quarterly tables), Inventory Management templates, Marketing Calendar (12 months), Social Media Content Planner, Order Fulfillment Checklist, Supplier Contact Sheet, Financial Dashboard (monthly P&L), Goal Setting framework. Dark navy #1E293B backgrounds, emerald #059669 accents, Oswald titles. | 60 min | Book 2 first 50 pages | K2.1 specs | ☐
12 | INSTAGRAM | I1 | I1.4 | Cross-post Video #2 Shorts + carousel | Upload V2 Short #1 as Instagram Reel + Canva cover + caption + Set 1 hashtags. Create Carousel: '5 Things About the Battle of Imphal' using V2 research → schedule. Upload to TikTok. Post 2 Stories: video teaser ('New video: The battle they tried to forget') + quiz sticker. | 20 min | Reel + carousel + TikTok + Stories | V2 Shorts + templates | ☐
══════ DAY 13 ══════
13 | KDP | K2 | K2.3 | Book 2 — complete interior + cover + submit | Finish remaining Book 2 pages (50-100 pages remaining). Design cover per K2.2 Business Niche blueprint: dark navy background, emerald accent bars, Oswald Bold title, Outfit subtitle. Download KDP cover template for Book 2 page count. Design full cover (front + spine + back). Export interior PDF + cover PDF. Submit to KDP: title, subtitle, pen name #2 from K1.3, 7 keywords from K1.4, 3 categories, price $12.99. | 90 min | Book 2 submitted to KDP | K2.1 + K2.2 specs | ☐
13 | INSTAGRAM | I1 | I1.4 | Continue daily rhythm | Cross-post V2 Short #2 as Reel. Post Fact Card from Video #2 ('150,000 Japanese soldiers marched toward a city most of the world had never heard of'). 2 Stories (behind-the-scenes: show archival photos you found during research). Engage: comment thoughtfully on 10 military history pages. | 15 min | Reel + Fact Card + Stories + engagement | Templates + V2 research | ☐
══════ DAY 14 ══════
14 | INSTAGRAM | I1 | I1.4 | Week 2 Instagram review + engagement push | Review Instagram Insights: which post got most saves? Most shares? Most profile visits? Note best hashtag set. Reply to all comments and DMs. Cross-post V2 Short #3 as Reel. Post 2 Stories with polls. Visit 10 history pages → leave genuine comments (not 'nice post' — ask questions, add facts). | 20 min | Week 2 analytics reviewed + engagement | 2 weeks of content | ☐
14 | YOUTUBE | Y3 | Y3.4 | Week 2 YouTube analytics review | Open YouTube Studio → Analytics: check Video #1 CTR (aim >4%), average view duration (aim >40%), traffic sources (how much from Reddit? Browse? Search?). Check Video #2 same metrics. Which performed better? Why? Reply to all new comments. Check Shorts performance (views, subs gained). Write down: 1 thing to improve, 1 thing working well. | 15 min | Analytics snapshot documented | 2 videos live | ☐
14 | KDP | K2 | K2.3 | Check Book 1 & 2 status | Check KDP dashboard: Book 1 should be live and potentially have sales data. Book 2 should be in review. If Book 1 has any sales: celebrate — proof of concept. If zero sales: normal for first 2 weeks, don't panic. Check listing quality: is description displaying correctly? Are categories right? | 5 min | Status check complete | Books submitted | ☐
══════ DAY 15 ══════
15 | YOUTUBE | Y2 | Y2.1 | Video #3 — research + script + assets | Topic: 'The Ghost Army — How Fake Tanks Won WW2'. Research: 23rd Headquarters Special Troops, inflatable tanks, sound trucks, radio deception, Operation Fortitude, specific missions in France/Germany, personnel (artists, radio operators, sound engineers), post-war secrecy (classified until 1996). Write 2,000-word script. Download 15+ images: inflatable tanks, dummy vehicles, Ghost Army soldiers, mission maps. | 90 min | Script #3 + 15 images | None | ☐
══════ DAY 16 ══════
16 | YOUTUBE | Y2 | Y2.2-Y2.4 | Video #3 — full production (record → edit → thumb) | Record voiceover. Master in Audacity. Edit full video in CapCut (this should be getting faster with practice — aim for 70 min edit). Create thumbnail: inflatable tank image + 'FAKE TANKS WON WW2' text + 'CLASSIFIED' red badge. Export everything. | 120 min | Video #3 complete (MP4 + thumb) | Script + assets | ☐
══════ DAY 17 ══════
17 | YOUTUBE | Y3 | Y3.1 | PUBLISH Video #3 + Shorts + promotion | Upload Video #3 with full metadata. Create and upload 3 Shorts. Promote to Reddit (r/MilitaryHistory, r/todayilearned — Ghost Army is perfect for TIL), Facebook groups, 1 Quora answer. This is your most 'viral potential' topic — inflatable tanks are inherently shareable. | 40 min | Video #3 + 3 Shorts live | Video #3 file | ☐
17 | INSTAGRAM | I1 | I1.4 | Video #3 Instagram + TikTok distribution | Carousel: '5 Things About the Ghost Army' (the inflatable tanks visual makes incredible carousel content). Cross-post best Short as Reel. Fact Card: 'In WW2, a top-secret unit used inflatable tanks and sound trucks to fool the entire German army.' TikTok: upload all 3 Shorts. Twitter: 5-tweet thread about the Ghost Army. | 25 min | Carousel + Reel + Fact Card + TikTok + Twitter | V3 Shorts + templates | ☐
══════ DAY 18 ══════
18 | KDP | K2 | K2.3 | Build Book 3 — Half Marathon Training Log | Book 3 (Half Marathon Training Log, $9.99) in Canva 6×9. Per K2.1 specs: 16-week training plan structure, weekly log pages (day, distance, time, pace, heart rate, notes), race day preparation checklist, nutrition tracking, injury log, personal records page, race route planning, 10K → half marathon bridge program. Red/charcoal/orange color scheme, Bebas Neue titles. Build complete interior (~110 pages). | 90 min | Book 3 interior complete | K2.1 specs | ☐
══════ DAY 19 ══════
19 | KDP | K2 | K2.3 | Book 3 — cover + submit + start Book 4 | Design Book 3 cover per K2.2 Running Niche blueprint: red/charcoal/orange, Bebas Neue Bold title, dynamic feel. Submit to KDP with keywords from K1.4. Begin Book 4 (Family Budget Tracker, $12.99): build interior with monthly budget sheets, expense categories, savings goals, debt payoff tracker, 52-week savings challenge. Aim to finish and submit Book 4 by Day 21. | 90 min | Book 3 submitted + Book 4 started | Book 3 interior | ☐
══════ DAY 20 ══════
20 | KDP | K2 | K2.3 | Finish Book 4 + submit | Complete Book 4 interior. Design cover (Business Niche scheme). Export and submit to KDP. You now have 4 books published or in review. | 60 min | Book 4 submitted — 4 books total | Book 4 interior | ☐
20 | YOUTUBE/IG | ALL | — | Week 3 analytics review — all 3 tracks | YouTube Studio: compare V1/V2/V3 CTR, view duration, subs gained per video. Instagram Insights: follower count, best post, saves rate. KDP dashboard: any sales? Check all 3 platforms. Write down: top performing content per platform, what to adjust, what to double down on. This is your first real data-driven review. | 20 min | Full analytics review documented | 3 weeks of content | ☐
══════ DAY 21 ══════
21 | INSTAGRAM | I1 | — | Instagram engagement + Stories + Reels | Continue daily rhythm: cross-post latest YouTube Short as Reel, 2-3 Stories (mix of facts, polls, behind-the-scenes), thoughtful engagement on 10 history pages. By now you should have 15+ posts on your grid. If follower count is below 100: increase Reel frequency to 1/day, engage more aggressively with community. | 15 min | Daily Instagram maintained | Ongoing | ☐
══════ DAY 22 ══════
22 | YOUTUBE | Y2 | Y2.1 | Video #4 — research + script | Topic: 'Why 80,000 Soldiers Surrendered — The Fall of Singapore 1942'. Research: Japanese invasion of Malaya, bicycle blitzkrieg, battle of Singapore, Percival's surrender (largest British surrender in history), 80,000 POWs, treatment of POWs, Changi prison, strategic failures, Churchill's 'worst disaster'. | 60 min | Script #4 complete | None | ☐
══════ DAY 23 ══════
23 | YOUTUBE | Y2-Y3 | Y2.2-Y3.1 | Video #4 — full production + publish | Record, edit, thumbnail, upload, shorts batch, promote. By Video #4, your workflow should be significantly faster — target 3 hours total production (down from 4+ for V1). Cross-post to Instagram (Reel + Carousel) and TikTok. | 180 min | Video #4 + 3 Shorts live | Script + assets | ☐
══════ DAY 24 ══════
24 | YOUTUBE | Y2 | Y2.1 | Video #5 — begin production | Topic: 'The Spy Princess — Noor Inayat Khan'. Research: SOE, Noor's background (Indian-American-French), training, deployment to occupied France, radio operations, betrayal, capture, Dachau. This is your espionage pillar (15% of content) — different tone from battle stories. More personal, intimate narration. | 60 min | Script #5 started | None | ☐
══════ DAY 25 ══════
25 | YOUTUBE | Y2-Y3 | Y2.1-Y3.1 | Video #5 — complete production + publish | Finish script, record, edit, thumbnail, publish, shorts, promote. Cross-post to Instagram + TikTok. 5 videos live on YouTube — you're past the 'quit zone'. | 180 min | Video #5 + 3 Shorts live (5 total videos) | Script + assets | ☐
══════ DAY 26 ══════
26 | INSTAGRAM | I1 | I1.4 | First collab attempt | Identify 3 military history Instagram pages with 5K-20K followers. DM each with a genuine collab proposal: 'Hey, I run @theforgottenfront covering untold military history stories. Would love to do a collab post — I can create a carousel about [topic they cover] and we can co-post it. Let me know!' Don't be pushy. 1 in 3 acceptance rate is great. | 15 min | 3 collab DMs sent | 15+ IG posts live | ☐
══════ DAY 28 ══════
28 | ALL | — | — | Month 1 comprehensive review — YouTube | Full YouTube audit: total views across all videos, total subscribers, best performing video (by views AND by retention%), best performing Short, CTR per video, traffic sources breakdown (search vs browse vs external), audience demographics. Compare against Achievement Matrix: which scenario are you in? Write 3 things to improve in Month 2. | 20 min | YouTube Month 1 report | 5 videos + 12 Shorts | ☐
══════ DAY 29 ══════
29 | ALL | — | — | Month 1 comprehensive review — KDP + Instagram | KDP: total sales across 4 books, which book sold most, any reviews yet, keyword ranking check (search your title on Amazon — where does it appear?). Instagram: follower count, total reach, best post type (Reel vs Carousel vs Fact Card), saves rate, non-follower reach %. Compare all against Achievement Matrix scenarios. Plan Month 2 adjustments. | 20 min | KDP + Instagram Month 1 report | 4 books + 20 IG posts | ☐
══════ DAY 30 ══════
30 | ALL | — | — | Month 2 planning + milestone celebration | Based on Month 1 data: plan next 4 video topics (Videos 6-9). Plan KDP Books 5-6 (which niches from K1.1?). Set Instagram Month 2 targets. Update link-in-bio with KDP book links. Review: are you on track for Probable scenario? If yes: maintain pace. If below: what's the bottleneck? If above: can you increase cadence? CELEBRATE: You have 5 YouTube videos, 4 KDP books, 20+ Instagram posts, and a real online business. | 30 min | Month 2 plan documented | Month 1 review complete | ☐

## Summary by Project
PROJECT & SUBPROJECT SUMMARY — 30-Day Sprint
Track | Project | Description | Status | Tasks | Est. Time
SETUP | — | All accounts, tools, folders, link-in-bio | Day 1 | 7 tasks | ~1.5 hrs
KDP | K2.3 | Book 1 Interior Production | Days 2-4 | 5 tasks | ~4 hrs
KDP | K2.4 | Book 1 Cover + Publish | Days 4-5 | 3 tasks | ~1.5 hrs
KDP | K2.3 | Book 2 Production + Submit | Days 12-13 | 2 tasks | ~2.5 hrs
KDP | K2.3 | Book 3 Production + Submit | Days 18-19 | 2 tasks | ~3 hrs
KDP | K2.3 | Book 4 Production + Submit | Days 19-20 | 1 task | ~1.5 hrs
YOUTUBE | Y2.1 | Video #1 Research + Script | Day 6 | 2 tasks | ~1.75 hrs
YOUTUBE | Y2.2-Y2.4 | Video #1 Production (edit+thumb) | Day 7 | 3 tasks | ~2.5 hrs
YOUTUBE | Y3.1 | Video #1 Publish + Shorts | Day 8 | 3 tasks | ~1 hr
YOUTUBE | Y2.1-Y3.1 | Video #2 Full Pipeline | Days 10-12 | 5 tasks | ~5 hrs
YOUTUBE | Y2.1-Y3.1 | Video #3 Full Pipeline | Days 15-17 | 3 tasks | ~5 hrs
YOUTUBE | Y2.1-Y3.1 | Video #4 Full Pipeline | Days 22-23 | 2 tasks | ~4 hrs
YOUTUBE | Y2.1-Y3.1 | Video #5 Full Pipeline | Days 24-25 | 2 tasks | ~4 hrs
INSTAGRAM | I1.1-I1.2 | Profile setup + templates + highlights | Days 1-3 | 3 tasks | ~1 hr
INSTAGRAM | I1.3-I1.4 | Cross-posting rhythm established | Days 8-30 | 12+ tasks | ~45 min/week
ALL | — | Week 2 Analytics Review | Day 14 | 2 tasks | ~35 min
ALL | — | Week 3 Analytics Review | Day 20 | 1 task | ~20 min
ALL | — | Month 1 Comprehensive Review | Days 28-30 | 3 tasks | ~1 hr